## Bill Tracker
Project | : Sattva City |  | Date: | 21.07.2025
Vendor | : Pragathi Landscapers LLP
WO NO | : 4300006116
WO Value | : Rs. 1,44,70,656.36/-
Nature of Work | : Landscape Works
RA Bill No | : 05
Bill Period | : 07.05.2025 to 04.07.2025
WORK BILL TRACKING CHART
S No | Particulars | Date | No of Days Taken | Reasons for Delay if any
A | PROJECTS/SITE QS/CONTRACTS DEPT.
1 | Document date | 05.07.2025
2 | Bill Received by Project In-charge | 16.07.2025
3 | Bill Received by Site QS | 16.07.2025
4 | Contractor QS/Reqd. Information/Attachment not available
5 | Other delays if any
6 | Amendment/Open WO request sent to Planning
7 | PR Raised by planning
8 | Amendment released by Contract/Purchase Dept
9 | Bill approved by Site In-charge
10 | Certified/SES Entry made by Site QS (1st Level) | 21.07.2025
B | BILLING, HO
1 | Bill Received at HO QS
2 | Bill Processed to Billing A/C
3 | SES 2nd level Release
4 | Tax Invoice Date
5 | Corrected Tax Invoice Received
6 | Parking Date
7 | Received duly approved
8 | Posting Date
9 | Handedover to Acct. Dept.
C | ACCOUNTS
1 | Cheque Signing List
2 | Cheque handedover to Vendor.
SAP WO | : 4300006116
SES NO | :
SAP Amount | :
Bill Period | : 07.05.2025 to 04.07.2025

## Checklist
Salarpuria Sattva Group
DOC No. |  | 21.07.2025 | Page 1 of 1
Service Invoice Checklist
Invoice Number:
Date: | 21.07.2025
Single Point of Contact Number
Project Name | : Sattva City
Project Manager | : Annappa S Chikkamani
S. No. | Document Name | Available | Remarks
A | Checklist for Invoicing
1 | Point of Contact (POC) / Work Order Number | a
Quantity Surveyor
2 | Billing Break Up (BBU) Codes - (Nature of Works) | a
3 | Three Way Match: BBU Quantity - Certified Quantity - Invoice Quantity | a
4 | Location of Invoicing | NA
5 | Reconciliation of Quantity Executed/ Pending Execution | NA
6 | Scope Change Note/ Quantity Amendment Note | NA
7 | BBU / Nature of Work Rates | a
8 | Ad-Hoc Payment | x
Billing & Audit
9 | Tax Rates as per Jurisdiction
10 | Advance Adjustment (If Applicable)
11 | Retention
12 | Hold Amount
13 | Car Policy
14 | BG's and Validity
15 | Advances
B | Service Documents
1 | Quantity Surveyor
2 | Approved Work Measurement Sheets | a
3 | Advance Adjustment (If Applicable) | NA
4 | Quality Inspection Reports (Pour Cards, Cube Test Reports etc.) | NA
5 | QC/Safety Clearance (If Applicable) | NA
6 | Material Reconciliation Report (if any) | NA
7 | Debit Notes | NA
8 | Approval of Extra Items | NA
9 | As-Built Drawings | NA
Billing & Audit
1 | Abstract Sheets
2 | Labour Cess Challans/Receipts
3 | PF/Employees State Insurance (ESI) Copies
4 | Labour License
5 | Minimum Wage Act Compliance Report
6 | Handover Protocols (If Applicable)
7 | Tax Exemption Certificate from Client (TDS, Others)
8 | Works Contract Tax Remittance against Declaration
C | For Raw Material Supplied
Quantity Surveyor
1 | Invoice | NA
2 | Test Certificates | NA
3 | Pre-dispatch clearance certificate | NA
4 | Weighbridge Slips | NA
D | For Price Variation Invoices
Contracts
1 | Schedule of Dates
2 | Schedule of Indices
3 | Calculation Sheet
E | Other Contract Specific Document Requirements
| Name | Designation | Signature
Prepared by | Chethan G A | Engineer-QS
Approved by
NA: Not applicable

## PRAG SUMMURY (hidden)
PROJECT :SATTVA CITY
CLIENT : SATTVA CITY PRIVATE LIMITED
CONTRACTOR : M/S PRAGATHI LANDSCAPERS LLP
WO NO: 4300006116/R1 DATED : 03-10-2024
NATURE OF WORK: HARDSCAPE WORKS |  |  | RA BILL-04
DATE: 14-07-2025
SL No. | DESCRIPTION | BOQ AMOUNT | PREVIOUS | CURRENT | CUMMULATIVE | REMARKS
1 | HARDSCAPE WORKS | 19856638.919 | 0 | 632733.4366 | 632733.4366
| SUB - TOTAL | 19856638.919 | 0 | 632733.4366 | 632733.4366
| GST @ 18% | 3574195.0054 | 0 | 113892.0186 | 113892.0186
| GRAND TOTAL | 23430833.9244 | 0 | 746625.4552 | 746625.4552

## PRAG SUM (hidden)
PROJECT :SATTVA CITY
CLIENT : SATTVA CITY PRIVATE LIMITED
CONTRACTOR : M/S PRAGATHI LANDSCAPERS LLP
WO NO: 4300006116/R1 DATED : 03-10-2024
NATURE OF WORK: HARDSCAPE WORKS |  |  | RA BILL-03
DATE: 06-05-2025
SL No. | DESCRIPTION | BOQ AMOUNT | PREVIOUS | CURRENT | CUMMULATIVE | REMARKS
1 | HARDSCAPE WORKS | 589247.24 | 0 | 632733.4366 | 632733.4366
| SUB - TOTAL | 589247.24 | 0 | 632733.4366 | 632733.4366
| GST @ 18% | 106064.5032 | 0 | 113892.0186 | 113892.0186
| GRAND TOTAL | 695311.7432 | 0 | 746625.4552 | 746625.4552

## PRAG SUMMURY
PROJECT :SATTVA CITY
CLIENT : SATTVA CITY PRIVATE LIMITED
CONTRACTOR : M/S PRAGATHI LANDSCAPERS LLP
WO NO: 4300006116/R1 DATED : 03-10-2024
NATURE OF WORK: HARDSCAPE WORKS |  |  | RA BILL-05 & FINAL
DATE: 23-10-2025
SL No. | DESCRIPTION | BOQ AMOUNT | PREVIOUS | CURRENT | CUMMULATIVE | REMARKS
1 | HARDSCAPE WORKS | 19856638.919 | 8162761.0845 | 996184.754 | 9158945.8385
2 | NT ITEMS | 589247.24 | 0 | 632733.4366 | 632733.4366
| SUB - TOTAL | 19856638.919 | 8162761.0845 | 1628918.1906 | 9791679.2751
| GST @ 18% | 3574195.0054 | 1469296.9952 | 293205.2743 | 1762502.2695
| GRAND TOTAL | 23430833.9244 | 9632058.0797 | 1922123.4649 | 11554181.5446

## Abstract
Project | : Sattva City
Vendor | : Pragathi Landscapers LLP
WO NO | : 4300006116
WO Value | : Rs. 1,44,70,656.36/-
Nature of Work | : Landscape Works
RA Bill No | : 05
Bill Period | : 07.05.2025 to 04.07.2025
ABSTRACT
Sr.No | Description | SAP CODE | Unit | BOQ Qty | Rate | Amount | Quantity |  |  | Amount |  |  | Remarks
[7 empty] | Previous | Present | Cumulative | Previous | Present | Cumulative
10 | Marketing office front area Hardscape
10 | LAND_BASE PREPARATION BASE PREPARATION WORKS Clearing and grubbing of top 150mm top soil including cutting, removing and disposing of all materials such as trees, bushes, shrubs, stumps, roots, grass, weeds, top organic soil etc. complete. | 55008371 | M2 | 6230.157 | 60 | 373809.42 | 269.4873 | 0 | 269.4873 | 16169.2392 | 0 | 16169.2392 |  | 5960.6697
20 | LAND_SUP/FlX_PIain Concrete M10 grade PCC WORKS (1:4:8) Providing and laying Plain cement concrete 1:4:8 mix of following to the depth at locations specified at all levels using river sand, graded granite aggregate of 20mm and down size including base preparation, compaction. levelling, all leads and lifts, curing and shuttering if necessary etc., complete as per drawings. (100mm thick PCC) | 55007038 | M3 | 623.016 | 4950 | 3083929.2 | 210.0148 | 0 | 210.0148 | 1039573.2247 | 0 | 1039573.2247 |  | 413.0012
30 | 55009582 LAND_SUP/FIX_GRANITE COBBLE HARDSCAPE WORKS Black flamed Granite Cobble Stone Providing & laying of Black Granite Cobble stones of 100X100mm over 50mm thick pcc bed to required shape, size and pattern .to required line, level, etc. all complete cost including of all materials at site, necessary earth compaction, all labour charges and other charges required to complete. Location - Driveway paving band (75mm thick) | 65000300 | M2 | 225 | 3230 | 726750 | 211.5 | 0 | 211.5 | 683145 | 0 | 683145 |  | 13.5
40 | 55009582 LAND_SUP/FIX_GRANITE COBBLE Same as above, for paving band (40mm thick)- Pedestrian walkway | 65000300 | M2 | 0.001 | 3230 | 3.23 |  | 0 |  | 0 | 0 | 0 |  | 0.001
50 | LAND_FIX_CONCRETE KERBS Precast Concrete Kerb Receiving and fixing of Precast Concrete kerbs of size 150mm thick of approved make, on cement concrete base of 1:3:6 mix as per dwg, cost including all materials at site, necessary earth excavation, all labour Charges and other necessary charges all as per drawings. Location- Along Driveway | 53003478 | M | 2318.5 | 475 | 1101287.5 | 1089.1808 | 22.66 | 1111.8408 | 517360.88 | 10763.5 | 528124.38 |  | 1206.6592
60 | LAND_FIX_FLUSH KERBS Flush Kerb Kerbs: Receiving and fixing of Concrete flush type kerbs of size 100x300x600mm of approved make with Matte Finish, on cement concrete base of 1:3:6mix as per dwg, cost including all materials at site, necessary earth excavation. all labour charges and other necessary charges all as per drawings. Location- Along Pedestrian walkway | 53003479 | M | 1364.75 | 450 | 614137.5 | 1143.7395 | 22.66 | 1166.3995 | 514682.775 | 10197 | 524879.775 |  | 198.3505 | 1292.24
70 | Land_sup/fix_pebbles Pebbles Supply and laying of "River washed Pebbles" of 40-50 mm dia or as per drawings. The quoted rate shall include the cost of supply, transport and laying in layers, pattern, etc., complete with cement mortor Location- Laid on waterbody drain | 55003457 | KG | 0.001 | 72 | 0.072 |  | 0 |  | 0 | 0 | 0 |  | 0.001
80 | LAND_FIX_BALCK GRANITE Granite Flooring Receiving and laying in position of approved Polished Jet Black Granite stone flooring of size 20mm thick as per selection laid over a bed of minimum 35mm thick cemen mortar 1:4 to the approved pattern as per the detail drawings. The joints shall be pointed with the matching cement based polymer grout with polished and unpolished surfaces of the granite slabs shall be finished with sealer coats as recommended by Laticrete/ Bal Endura/ Aqua mix or approved equivalent make and complete. Pre-polished granite slabs shall have the edges machine cut to precise sizes to produce very fine joints. All the exposed edges of the flooring shall be machine polished to profiles as per the detail drawings. This also includes providing top covering over the polythene sheets for the entire flooring to protect against scratches etc. Location- Water Feature | 55007750 | M2 | 0.001 | 1065 | 1.065 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.001
90 | F/C_FIX_Granite Cladding Granite Cladding Receving and fixing in position of 40-50mm thick approved Polished Jet Black Granite stone cladding to walls, columns and other vertical faces as called for fixed over a backing of avg 25mm thick cement mortar 1:4 and Grey Cement paste CM 1:1 to pattern as per the detail drawings. The joints shall be pointed with the matching cement based polymer grout by Laticrete or approved equivalent make and complete. Rate includes necessary scaffolding, staging, curing, etc., complete as per the instructions of the Architect / Engineer in charge. The slabs shall have the edges machine cut and polished to produce very fine joints. The cladding shall be polished if required to give the final finish as desired by architects. Rate to include wastage, providing necessary V-grooves in the joints, Granite insets in different vertical and horizontal levels/ plane as per the detail drawings if required. Location- Water Feature Location- Planter | 52000566 | M2 | 0.001 | 1136 | 1.136 |  | 0 |  | 0 | 0 | 0 |  | 0.001
100 | F/C_FlX_Granite Cladding above line item Location- Planter | 52000566 | M2 | 0.001 | 1136 | 1.136 |  | 0 |  | 0 | 0 | 0 |  | 0.001
110 | LAND_GRANITE COPING Granite Coping Receiving & Laying of 40mm thick Polished Jet Black Granite, flamed finish coping with full nosing, edge polishing on both sides in CM 1:4 over minimum thickness of 25-30mm over the masonry/RCC. The rate shall include cutting required size. laying, grouting, curing. edge finishing etc complete. Location- Water Feature 300mm width | 55005650 | M | 0.001 | 1080 | 1.08 |  | 0 |  | 0 | 0 | 0 |  | 0.001
120 | LAND_GRANITE COPING above line item Location- Planter 450 mm width | 55005650 | M | 0.001 | 1165 | 1.165 |  | 0 |  | 0 | 0 | 0 |  | 0.001
130 | LAND_FIX_CONCRETE PAVERS Concrete Pavers Receving and fixing of Concrete Pavers blocks of 200 x 100 X 80mm. laid over 35mm thick cemen mortar 1:4 , joints to be cleaned, curing, cleaning, etc. to required line, level, etc. all complete cost including of all materials at site, necessary earth compaction, all labour charges and other charges required to complete. Color- Dark Grey. For Pedestrian walkway -80mm Thick Paver | 53003477 | M2 | 962.628 | 410 | 394677.48 | 771.5695 | 1066.5002 | 1838.0697 | 316343.4989 | 437265.0751 | 753608.574 |  | -875.4417
140 | Land_SUP/Lay_Brush Finish Concrete Broom Finish Concrete Providing and laying of Concrete in M25 grade screed with water cement ratio of 0.5 of average thickness of 150mm as directed during execution and shall be laid in bays of suitable sizes and to required slope in a alternate panel fashion and neatly finished with power trowelled and lines drawn as directed, Screed Concrete shall be laid in One layer with 10 mm and down size graded stone aggregates This layer shall be thoroughly tamped, spread,incIusive of Power trowelled and finished smooth with E floating coat of neat cement. No dry cement shall be allowed to be used for finishing the surface. The surface shall be kept well watered after it is dry for a period of 8 days. Cost Shall be inclusive of making sub base area clean by removing dead mortor/concrete by chipping and laying the concrete in panels o 4mx4m providing suitable grooves. The surface Shall be finished with troll finish/broom finish etc complete. The construction joint shall be cut using diamond bit wheel for a width of 3 to 4mm and a depth of 30mm within 20 to 30 hours of concreting, no delay shall be acceptable. On curing and drying of the concrete the construction joints have to be filled with sealants as per manufacturers specification. Location- Entry Ramp | 55004902 | M2 | 0.001 | 5800 | 5.8 |  | 0 |  | 0 | 0 | 0 |  | 0.001
150 | LAND_POW ER TROWEL Power Trowel with broom finish for above item | 55009607 | M2 | 1051.058 | 115 | 120871.67 | 2467.1711 | 620.7699 | 3087.941 | 283724.6722 | 71388.5407 | 355113.2129 |  | -2036.883
160 | LAND_GROOVE CUTTING Groove cutting for above item | 55007653 | M | 210.8 | 60 | 12648 | 357.8 | 0 | 357.8 | 21468 | 0 | 21468 |  | -147
20 | NT ITEMS-26-14127 | [12 empty] | 0
10 | Land_Sup/Fix_Granular Sub Base Providing & laying of Granular Sub-base with Coarse Graded material (Table:- 400-2) compacted thickness of 150mm by providing, laying, spreading and compacting , spreading in uniform layers with motor grader on prepared surface, mixing by mix in place method with rotavator at OMC, and compacting with vibratory roller 8-10 tonne to achieve the desired density of 98% including protection of edges of GSB layer, cost of all materials, labour, hire charges of machinery, loading & Unloading, all lead and lift etc., complete. as per the directions of eng-in- charge of work in accordance Technical Specification | 55007561 | M3 | 1654.823 | 2050 | 3392387.15 | 939.1261 | 3.9111 | 943.0372 | 1925208.5051 | 8017.7929 | 1933226.298 | 1082.4805 | 711.7858
20 | Land_SUP/FlX_Wet Mix Macadam Providing,laying 2 layers WMM (Wet mix macadem) with Stone aggregate with approved quality of 20mm down grade and quarry dust, well packed, correct to level. The surface shall be consolidated by 8 to 10 Tonne power road roller after spreading of well compacted earth or boulder soling as the sub base etc., complete. The finish consolidated thickness shall be 150mm. | 55007682 | M3 | 945.768 | 2325 | 2198910.6 | 649.5511 | 0 | 649.5511 | 1510206.3585 | 0 | 1510206.3585 | 1080.15 | 296.2169
30 | Land__SUP/FILL_sweet earth fill Shifting and Filling of existing soil within the site for planter box and any other location manually with consolidation. | 55002290 | M3 | 1197.126 | 240 | 287310.24 | 1430.4246 | 69.2444 | 1499.669 | 343301.901 | 16618.667 | 359920.568 |  | -302.543
40 | Receiving & fixing reinforcement for RCC work with high yield strength ribbed cold twisted for steel of various diameters of grade Fe-500 confirming to BIS specificationincluding cutting, bending, fabricating, & placing in position according to drawings & binding the reinforcement with the use of 18 guage MS binding wire of double fold & providing precast cement cover blocks for main reinforecements to ensure specified cover according to relevant IS code. The measurements will be in accordance with the code IS: 1200. Note: Unless noted otherwise the measurements in accordance with IS: 1200 or equivalent BS codes. However reinforcement shall be measured only in lengths of bars as actually placed in position on standard weight basis, no allowance being made in the weight for rolling margin. Authorised laps and splices only will be measured. Chairs of any shape and profile, Spacer bar of any bshape & profile, cover block, wastage & binding wire will not be measured & shall be included in the quote rates. Quoted rate shall be deemed to have considered the above stipulation. | 55010117 | KG | 27859.056 | 16 | 445744.896 | 7260.4753 | 4336.9927 | 11597.468 | 116167.604 | 69391.8838 | 185559.4878 |  | 16261.588
50 | CHAMBER WORK (900*900* Depth up to 1.5mt) Excavation, Compaction, PCC Providing and laying 6 inch block masonry in cement mortar 1:3 (1 cement : 3 coarse sand) of in true line level and plumb for walls, with necessary scaffolding, curing etc., Providing, applying of External & internal plastering in c.m. 1:3, 15-20mm thick Single Coat including necessary scaffolding, as per design, curing and hacking to the surfaces & finish including chamber cover fixing on the top etc., complete. (Note: chamber cover supply by sattva). | 55008193 | NOS | 11 | 17400 | 191400 | 11 | 8 | 19 | 191400 | 139200 | 330600 |  | -8
60 | CHAMBER WORK (450*450* Depth up to 0.7mt) Excavation, Compaction, PCC Providing and laying 6 inch block masonry in cement mortar 1:3 (1 cement : 3 coarse sand) of in true line level and plumb for walls, with necessary scaffolding, curing etc., Providing, applying of External & internal plastering in c.m. 1:3, 15-20mm thick Single Coat including necessary scaffolding, as per design, curing and hacking to the surfaces & finish including chamber cover fixing on the top etc., complete. (Note: chamber cover supply by sattva) | 55008193 | NOS | 23 | 5200 | 119600 | 0 | 0 | 0 | 0 | 0 | 0 |  | 23
70 | CHAMBER WORK (600*600* Depth up to 01mt) Excavation, Compaction, PCC Providing and laying 6 inch block masonry in cement mortar 1:3 (1 cement : 3 coarse sand) of in true line level and plumb for walls, with necessary scaffolding, curing etc., Providing, applying of External & internal plastering in c.m. 1:3, 15-20mm thick Single Coat including necessary scaffolding, as per design, curing and hacking to the surfaces & finish and including chamber cover fixing on the top etc., complete. (Note: chamber cover supply by sattva) | 55006453 | NOS | 4 | 8500 | 34000 | 4 | 0 | 4 | 34000 | 0 | 34000 |  | 0
80 | CHAMBER WORK (750*750* Depth up to 01mt) Excavation, Compaction, PCC Providing and laying 6 inch block masonry in cement mortar 1:3 (1 cement : 3 coarse sand) of in true line level and plumb for walls, with necessary scaffolding, curing etc., Providing, applying of External & internal plastering in c.m. 1:3, 15-20mm thick Single Coat including necessary scaffolding, as per design, curing and hacking to the surfaces & finish including chamber cover fixing on the top etc., complete. (Note: chamber cover supply by sattva) | 55008193 | NOS | 4 | 10000 | 40000 | 4 | 0 | 4 | 40000 | 0 | 40000 |  | 0
90 | CHAMBER WORK (300*300* Depth up to 0.1mt) Excavation, Compaction, PCC Providing and laying 6 inch block masonry in cement mortar 1:3 (1 cement : 3 coarse sand) of in true line level and plumb for walls, with necessary scaffolding, curing etc., Providing, applying of External & internal plastering in c.m. 1:3, 15-20mm thick Single Coat including necessary scaffolding, as per design, curing and hacking to the surfaces & finish including chamber cover fixing on the top etc., complete. (Note: chamber cover supply by sattva) | 55008193 | NOS | 28 | 5500 | 154000 | 12 | 18 | 30 | 66000 | 99000 | 165000 |  | -2
100 | Receiving and laying controlled Reinforced Cement Concrete of M30 grade at all levels and heights specified below using ordinary Portland cement of grade 43 from approved manufacturer, river sand, 20mm and down size coarse aggregates, necessary admixtures approved by Consultants (Conplast SP-430SRV from Fosroc or equivalent), including all leads and lifts, pumping using line pump or boom placer, vibrating/compaction, scaffolding wherever necessary, all lead and lifts, tools & Plants, pumping the concrete to all levels, curing etc. complete but excluding cost of reinforcement and formwork, centering, shuttering. Depending on the size and location, the maximum depth of concreting will be decided by Engineer in casting at a time. | 55008466 | M3 | 1071.98 | 1100 | 1179178 | 494.554 | 122.1294 | 616.6834 | 544009.4259 | 134342.2945 | 678351.7204 |  | 455.2966
| Total Amount |  |  |  |  | 14470656.34 |  |  |  | 8162761.0845 | 996184.754 | 9158945.8385 |  | 0
30 | NT ITEMS-25-15179 | [12 empty] | 0
1 | Waterproofing works
40 | 52008807 WP_ SUP/FIX_EXPANSION BOARD Supply and fixing of 25mm thick separation board of silplex capell HD-100 Soft board with 12mm dia dowell bars and 20mm PVC pipe with closed end filled with Grease with all material , labour and lead and lift complete as per specification. | 995453 | M | 34 | 1060 | 36040 |  | 84.3 | 84.3 |  | 89358 | 89358
2 | Flooring / Cladding
20 | F/C_FIX_Granite Flooring 40MM THICK STEEL GREY FLAMED FINISH GRANITE FLOORING-Machine cut, straight edge, with paper joint and 10mm wide 8mm deep recessed pointed groove joint between different granites, as per landscape architects details. laid over the CM 1:6mix cost including of all materials at site, all labour charges and other charges required to complete. Material Supplied by Sattva. | 995474 | M2 | 99.92 | 1466 | 146482.72 |  | 99.9151 | 99.9151 |  | 146475.5949 | 146475.5949
3 | Fabrication works
10 | 53000664 FAB_SUP/FIX_Saucer Drain RECEVING AND LAYING OF SAUCER DRAIN 600*300*125 MM Thick of approved make, on cement concrete base of 1:3:6 mix as per dwg, cost including all materials at site, necessary earth excavation, all labour Charges and other necessary charges all as per drawings. | 995442 | M | 307.47 | 400 | 122988 |  | 307.4677 | 307.4677 |  | 122987.08 | 122987.08
4 | Landscape
30 | 55001982 Land_SUP/FIX_polyethylene Modular sheet Providing and laying 300 micron High Density Polyethylene (HDPE) sheet below concrete pavement including all materials and labour complete |  | M2 | 2627.19 | 108 | 283736.52 |  | 2536.2293 | 2536.2293 |  | 273912.7617 | 273912.7617
| Total Amount |  |  |  |  | 589247.24 |  |  |  |  | 632733.4366 | 632733.4366 |  | 0

## NT MEAS
NON-TENDERED ITEMS
MEASUREMENT BACK UP
SL.NO | DESCRIPTION | UNIT | NOS | L | B | D | QTY | REMARKS
NT-01 | SAUCER DRAIN | RMT
RA BILL-02
AREA-01 | MARKETING OFFICE DROP OFF |  | 1 | 50.0706 |  |  | 50.0706 | 50070.6
|  |  | 1 | 18.7304 |  |  | 18.7304 | 18730.4
RA BILL-03
AREA-01 | MAIN DRIVEWAY AREA |  | 1 | 120.011 |  |  | 120.011 | 120011
RA BILL-04
AREA-01 | MAIN DRIVEWAY AREA |  | 1 | 40.0109 |  |  | 40.0109 | 40010.9
RA BILL-04
AREA-01 | MAIN DRIVEWAY AREA |  | 1 | 40.0109 |  |  | 40.0109 | 40010.9
AREA-02 | ROUNDABOUT AREA |  | 1 | 22.815 |  |  | 22.815 | 22815
AREA-03 | ROUNDABOUT AREA |  | 1 | 15.8189 |  |  | 15.8189 | 15818.9
| TOTAL | [5 empty] | 307.4677 | RMT | 520.7833
SL.NO | DESCRIPTION | UNIT | NOS | L | B | D | QTY | REMARKS
NT-02 | 40MM THICK STEEL GREY FLAMED FINISH GRANITE FLOORING | SQM
RA BILL-02
AREA-01 | MARKETING OFFICE DROP OFF |  | 1 | 99.9151 |  |  | 99.9151 | 99915139.8
| TOTAL | [5 empty] | 99.9151 | SQM
SL.NO | DESCRIPTION | UNIT | NOS | L | B | D | QTY | REMARKS
NT-03 | HDPE SHEET 600 MICRON BELOW M30 CONCRETE | SQM
RA BILL-02
AREA-01 | CAR PARKING AREA |  | 1 | 299.7644 |  |  | 299.7644 | 299764425.8
RA BILL-03
RA BILL-04
AREA-01 | MAIN DRIVEWAY 1 SIDE |  | 1 | 160 | 4.7 |  | 752
AREA-02 | ROUNDABOUT AREA |  | 1 | 335.1469 |  |  | 335.1469 | 335146877.1
| DEDUCTION OF COBBLE AREA |  | -1 | 8.0101 |  |  | -8.0101 | 8010131.9
|  |  | -1 | 1.2051 |  |  | -1.2051 | 1205132
|  |  | -1 | 0.86387 |  |  | -0.86387 | 863868.3
|  |  | -1 | 6.9739 |  |  | -6.9739 | 6973889.3
|  |  | -1 | 0.90084 |  |  | -0.90084 | 900844.8
|  |  | -1 | 4.4952 |  |  | -4.4952 | 4495217.4
|  |  | -1 | 3.28 |  |  | -3.28 | 3279989.6
|  |  | -1 | 5.891 |  |  | -5.891 | 5890957.3
|  |  | -1 | 7.5177 |  |  | -7.5177 | 7517703.2
|  |  | -1 | 4.6961 |  |  | -4.6961 | 4696141.6
|  |  | -1 | 2.3183 |  |  | -2.3183 | 2318274.4
|  |  | -1 | 4.4896 |  |  | -4.4896 | 4489566
|  |  | -1 | 2.5484 |  |  | -2.5484 | 2548396.5
AREA-03 | ROUNDABOUT AREA |  | 1 | 273.1111 |  |  | 273.1111 | 273111083.4
| DEDUCTION OF COBBLE AREA |  | -1 | 5.8687 |  |  | -5.8687 | 5868693.3
|  |  | -1 | 6.7479 |  |  | -6.7479 | 6747940.4
|  |  | -1 | 3.457 |  |  | -3.457 | 3457034.8
|  |  | -1 | 2.366 |  |  | -2.366 | 2365996.1
|  |  | -1 | 5.4874 |  |  | -5.4874 | 5487377.5
|  |  | -1 | 6.6297 |  |  | -6.6297 | 6629714.1
|  |  | -1 | 2.8848 |  |  | -2.8848 | 2884835.1
|  |  | -1 | 3.6484 |  |  | -3.6484 | 3648357.5
|  |  | -1 | 0.67741 |  |  | -0.67741 | 677411.8
AREA-04 | CAR PARKING AREA DRIVEWAY |  | 1 | 215.1644 |  |  | 215.1644 | 215164361.2
AREA-01 | MAIN DRIVEWAY AREA |  | 1 | 160 | 4.7 |  | 752
| TOTAL | [5 empty] | 2536.2293 | SQM
NT-04 | Supply and fixing of 25mm thick separation board of silplex capell HD-100 Soft board with 12mm dia dowell bars and 20mm PVC pipe with closed end filled with Grease with all material , labour and lead and lift complete as per specification.
RA BILL-04
| DRIVEWAY AREA |  | 8 | 4.7 |  |  | 37.6
| PARKING AREA |  | 2 | 6 |  |  | 12
|  |  | 1 | 4.7 |  |  | 4.7
| ROUNDABOUT AREA |  | 1 | 30 |  |  | 30
| TOTAL | [5 empty] | 84.3 | RMT

## M BOOK
Project | : Sattva City
Vendor | : Pragathi Landscapers LLP
WO NO | : 4300006116
WO Value | : Rs. 1,44,70,656.36/-
Nature of Work | : Landscape Works
RA Bill No | : 05
Bill Period | : 07.05.2025 to 04.07.2025 |  |  |  |  | DATE:23-10-2025
MEASUREMENT BACK UP-RA BILL-05
SL.NO | DESCRIPTION | UNIT | NOS | L | B | D | QTY | REMARKS
10 | Land_Sup/Fix_Granular Sub Base Providing & laying of Granular Sub-base with Coarse Graded material (Table:- 400-2) compacted thickness of 150mm by providing, laying, spreading and compacting , spreading in uniform layers with motor grader on prepared surface, mixing by mix in place method with rotavator at OMC, and compacting with vibratory roller 8-10 tonne to achieve the desired density of 98% including protection of edges of GSB layer, cost of all materials, labour, hire charges of machinery, loading & Unloading, all lead and lift etc., complete. as per the directions of eng-in- charge of work in accordance Technical Specification
RA BILL-01
AREA-01 | DRIVEWAY FROM ROUND ABOUT TOWARD ENTRACE AREA | CUM | 1 | 1195.8288 |  | 0.15 | 179.3743 | 1195828795.8
AREA-02 | PARKING AREA-PATHWAY |  | 1 | 352.1408 |  | 0.15 | 52.8211 | 352140810.1
| PLANTING AREA DEDUCTIONS |  | -1 | 31.5394 |  | 0.15 | -4.7309 | 31539406.1
AREA-03 | PARKING AREA |  | 1 | 821.298 |  | 0.15 | 123.1947 | 821297964.1
AREA-2A | PARKING AREA-KERB BASE GSB |  | 1 | 278.7148 | 0.4 | 0.15 | 16.7229 | 282544.8
| PARKING AREA-KERB BASE GSB |  | 1 | 23.7206 | 0.4 | 0.15 | 1.4232 | 23720.6
AREA-3A | PARKING AREA-KERB BASE GSB |  | 1 | 169.7952 | 0.4 | 0.15 | 10.1877 | 169795.2
RA BILL-02
AREA-01 | MARKETING OFFICE DROP OFF |  | 1 | 408.5099 |  | 0.15 | 61.2765 | 408509938.6
| MEDIAN DEDUCTION |  | -1 | 42.793 |  | 0.15 | -6.4189 | 42792993
AREA-02 | DRIVEWAY BESIDE PATHWAY |  | 1 | 113.2032 |  | 0.15 | 16.9805 | 113203236.2
AREA-03 | PARKING AREA PEDESTRIAN WALKWAY |  | 1 | 79.7488 |  | 0.15 | 11.9623 | 79748774
AREA-04 | MARKETING OFFICE DROP OFF PATHWAY |  | 1 | 124.335 |  | 0.15 | 18.6503 | 124335048.3
| MARKETING OFFICE DROP OFF PATHWAY |  | 1 | 35.4017 |  | 0.15 | 5.3103 | 35401721.8
AREA-05 | MARKETING OFFICE DROP OFF GRANITE AREA |  | 1 | 99.8273 |  | 0.15 | 14.9741 | 99827298.1
AREA-06 | MARKETING OFFICE WALKWAY |  | 1 | 56.0323 |  | 0.15 | 8.4048 | 56032303.6
AREA-07 | DRIVEWAY AREA |  | 1 | 878.6942 |  | 0.15 | 131.8041 | 878694231.6
AREA-08 | ROUND ABOUT |  | 1 | 480.0996 |  | 0.15 | 72.0149 | 480099596.1
KERB AREA GSB
450MM KERB Below
AREA-02 | MARKETING OFFICE AREA ENTRANCE |  | 1 | 51.8133 | 0.4 | 0.15 | 3.1088 | 51813.3
|  |  | 1 | 20.5444 | 0.4 | 0.15 | 1.2327 | 20544.4
AREA-03 | ROUND ABOUT AREA |  | 1 | 83.3172 | 0.4 | 0.15 | 4.999 | 93317.2
AREA-04 | DRIVEWAY BESIDE WALKWAY |  | 1 | 132.9259 | 0.4 | 0.15 | 7.9756 | 132925.9 | 118
AREA-05 | DRIVEWAY BETWEEN PLANTER |  | 1 | 259.6208 | 0.4 | 0.15 | 15.5772 | 259620.8
AREA-06 | PARKING AREA KERB |  | 1 | 20.7902 | 0.4 | 0.15 | 1.2474 | 20790.2
|  |  | 1 | 56.0082 | 0.4 | 0.15 | 3.3605 | 56008.2
300MM KERB
AREA-01 | MARKETING OFFICE AREA WALKWAY |  | 1 | 51.6025 | 0.4 | 0.15 | 3.0962 | 51602.5
|  |  | 1 | 49.1748 | 0.4 | 0.15 | 2.9505 | 49174.8
AREA-07 | PARKING AREA KERB |  | 1 | 44.2927 | 0.4 | 0.15 | 2.6576 | 44292.7
|  |  | 1 | 45.6837 | 0.4 | 0.15 | 2.741 | 45683.7
AREA-08 | PARKING AREA KERB |  | 1 | 16.7563 | 0.4 | 0.15 | 1.0054 | 16756.3
|  |  | 1 | 16.6063 | 0.4 | 0.15 | 0.99638 | 16606.3
AREA-09 | DRIVEWAY BESIDE WALKWAY |  | 1 | 50.0412 | 0.4 | 0.15 | 3.0025 | 50041.2
|  |  | 1 | 50.1043 | 0.4 | 0.15 | 3.0063 | 50104.3
AREA-10 | MARKETING OFFICE AREA ENTRANCE |  | 1 | 59.8166 | 0.4 | 0.15 | 3.589 | 59816.6
|  |  | 1 | 52.3787 | 0.4 | 0.15 | 3.1427 | 52378.7
AREA-11 | MARKETING OFFICE AREA ENTRANCE |  | 1 | 12.2146 | 0.4 | 0.15 | 0.73288 | 12214.6
|  |  | 1 | 12.5692 | 0.4 | 0.15 | 0.75415 | 12569.2
SAUCER DRAIN
AREA-01 | MARKETING OFFICE DROP OFF |  | 1 | 50.0706 | 0.4 | 0.15 | 3.0042 | 50070.6
|  |  | 1 | 18.7304 | 0.4 | 0.15 | 1.1238 | 18730.4
RA BILL-03
AREA-01 | CARPARKING AREA PEDESTRIAN WALKWAY |  | 1 | 52.5259 |  | 0.15 | 7.8789 | 52525888.7
AREA-02 | MARKETING OFFICE NORTHSIDE WALKWAY |  | 1 | 97.2358 |  | 0.15 | 14.5854 | 97235765
| Pending area dedu |  | -1 | 3 | 1.2 | 0.15 | -0.54
AREA-03 | CARPARKING DRIVEWAY AREA |  | 1 | 216.521 |  | 0.15 | 32.4782 | 216521012
RABILL-04
AREA-01 | ROUNDABOUT AREA |  | 1 | 393.8507 |  | 0.15 | 59.0776 | 393850678.2
AREA-02 | NEAR MARKETING OFFICE PAVERS AREA |  | 1 | 55.0172 |  | 0.1 | 5.5017 | 55017173.5
AREA-03 | MAIN DRIVEWAY BESIDE PATHWAY |  | 1 | 43.2451 |  | 0.15 | 6.4868 | 43245087
AREA-04 | MAIN DRIVEWAY ENTRY SIDE AREA |  | 1 | 202.6798 |  | 0.15 | 30.402 | 202679801.2
RA BILL-05
| INSIDE MARKETING OFFICE PLANTING AREA |  | 1 | 26.0741 |  | 0.15 | 3.9111 | 26074123.2
| TOTAL | [5 empty] | 943.0372 | CUM
50 | LAND_FIX_CONCRETE KERBS Precast Concrete Kerb Receiving and fixing of Precast Concrete kerbs of size 150mm thick of approved make, on cement concrete base of 1:3:6 mix as per dwg, cost including all materials at site, necessary earth excavation, all labour Charges and other necessary charges all as per drawings. Location- Along Driveway | RMT
RA BILL-01
AREA-02 | PARKING AREA |  | 1 | 169.7952 |  |  | 169.7952 | 169795.2
RA BILL-02
AREA-02 | MARKETING OFFICE AREA ENTRANCE |  | 1 | 51.8133 |  |  | 51.8133 | 51813.3
|  |  | 1 | 20.5444 |  |  | 20.5444 | 20544.4
AREA-03 | ROUND ABOUT AREA |  | 1 | 83.3172 |  |  | 83.3172 | 93317.2
AREA-04 | DRIVEWAY BESIDE WALKWAY |  | 1 | 132.9259 |  |  | 132.9259 | 132925.9
AREA-05 | DRIVEWAY BETWEEN PLANTER |  | 1 | 259.6208 |  |  | 259.6208 | 259620.8
AREA-06 | PARKING AREA KERB |  | 1 | 20.7902 |  |  | 20.7902 | 20790.2
|  |  | 1 | 56.0082 |  |  | 56.0082 | 56008.2
RA BILL-03
AREA-01 | DRIVEWAY NEAR ROUND ABOUT AREA |  | 1 | 9.79 |  |  | 9.79 | 9790
AREA-03 | CARPARKING DRIVEWAY AREA |  | 1 | 49.9087 |  |  | 49.9087 | 49908.7
RA BILL-04
AREA-01 | DRIVEWAY BESIDE KERB |  | 1 | 27.0119 |  |  | 27.0119 | 27011.9
AREA-02 | DRIVEWAY BETWEEN PLANTER |  | 2 | 27.0921 |  |  | 54.1842 | 27092.1
AREA-03 | DRIVEWAY NEAR ROUND ABOUT AREA |  | 1 | 8.2681 |  |  | 8.2681 | 8268.1
AREA-05 | ROUNDABOUT NORTHEAST SIDE |  | 1 | 16.3623 |  |  | 16.3623 | 16362.3
AREA-06 | AROUND CYCLE PARKING AREA |  | 1 | 28.0798 |  |  | 28.0798 | 28079.8
AREA-09 | MARKETING OFFICE FRONTSIDE CENTRE MEDIAN |  | 1 | 42.3377 |  |  | 42.3377 | 42337.7
AREA-11 | MAIN DRIVEWAY EXIT SIDE AREA |  | 1 | 51.0857 |  |  | 51.0857 | 51085.7
AREA-12 | CYCLE PARKING AREA ENTRY SIDE |  | 1 | 7.3372 |  |  | 7.3372 | 7337.2
RA BILL-05
AREA-01 | DRIVEWAY BESIDE KERBSTONE WORK |  | 1 | 22.66 |  |  | 22.66
| TOTAL | [5 empty] | 1111.8408 | RMT
60 | LAND_FIX_FLUSH KERBS Flush Kerb Kerbs: Receiving and fixing of Concrete flush type kerbs of size 100x300x600mm of approved make with Matte Finish, on cement concrete base of 1:3:6mix as per dwg, cost including all materials at site, necessary earth excavation. all labour charges and other necessary charges all as per drawings. Location- Along Pedestrian walkway | RMT
RA BILL-01
AREA-01 | PARKING AREA-PATHWAY | RMT | 1 | 278.7148 |  |  | 278.7148 | 282544.8
|  | RMT | 1 | 23.7496 |  |  | 23.7496 | 23749.6
RA BILL-02
AREA-01 | MARKETING OFFICE AREA WALKWAY |  | 1 | 51.6025 |  |  | 51.6025 | 51602.5
|  |  | 1 | 49.1748 |  |  | 49.1748 | 49174.8
AREA-07 | PARKING AREA KERB |  | 1 | 44.2927 |  |  | 44.2927 | 44292.7
|  |  | 1 | 45.6837 |  |  | 45.6837 | 45683.7
AREA-08 | PARKING AREA KERB |  | 1 | 16.7563 |  |  | 16.7563 | 16756.3
|  |  | 1 | 16.6063 |  |  | 16.6063 | 16606.3
AREA-09 | DRIVEWAY BESIDE WALKWAY |  | 1 | 50.0412 |  |  | 50.0412 | 50041.2
|  |  | 1 | 50.1043 |  |  | 50.1043 | 50104.3
AREA-10 | MARKETING OFFICE AREA ENTRANCE |  | 1 | 59.8166 |  |  | 59.8166 | 59816.6
|  |  | 1 | 52.3787 |  |  | 52.3787 | 52378.7
AREA-11 | MARKETING OFFICE AREA ENTRANCE |  | 1 | 12.2146 |  |  | 12.2146 | 12214.6
|  |  | 1 | 12.5692 |  |  | 12.5692 | 12569.2
RA BILL-03
AREA-02 | CARPARKING PEDESTRIAN WALKWAY |  | 1 | 9.6129 |  |  | 9.6129 | 9612.9
|  |  | 1 | 7.6281 |  |  | 7.6281 | 7628.1
|  |  | 1 | 1.25 |  |  | 1.25 | 1250
AREA-04 | MARKETING OFFICE NORTHSIDE WALKWAY |  | 1 | 79.5888 |  |  | 79.5888 | 79588.8
|  |  | 1 | 9.8824 |  |  | 9.8824 | 9882.4
|  |  | 1 | 66.7691 |  |  | 66.7691 | 66769.1
RA BILL-04
AREA-04 | MARKETING OFFICE NORTHSIDE |  | 1 | 17.7081 |  |  | 17.7081 | 17708.1
AREA-04 | MARKETING OFFICE NORTHSIDE |  | 1 | 18.6321 |  |  | 18.6321 | 18632.1
AREA-08 | MARKETING OFFICE PEDESTRIAN WALKWAY |  | 1 | 22.6265 |  |  | 22.6265 | 22626.5
AREA-08 | MARKETING OFFICE PEDESTRIAN WALKWAY |  | 1 | 24.4818 |  |  | 24.4818 | 24481.8
AREA-10 | DRIVEWAY BESIDE WALKWAY |  | 1 | 121.8544 |  |  | 121.8544 | 121854.4
RA BILL-05
AREA-02 | DRIVEWAY BESIDE KERBSTONE WORK |  | 1 | 22.66 |  |  | 22.66
| TOTAL | [5 empty] | 1166.3995 | RMT
20 | LAND_SUP/FlX_PIain Concrete M10 grade PCC WORKS (1:4:8) Providing and laying Plain cement concrete 1:4:8 mix of following to the depth at locations specified at all levels using river sand, graded granite aggregate of 20mm and down size including base preparation, compaction. levelling, all leads and lifts, curing and shuttering if necessary etc., complete as per drawings. (100mm thick PCC)
RA BILL-01
AREA-1A | PARKING AREA-PATHWAY KERB PLUGGING |  | 1 | 278.7148 | 0.3 | 0.075 | 6.2711 | 282544.8 | MANNUAL MIX
|  |  | 1 | 23.7496 | 0.3 | 0.075 | 0.53437 | 23749.6
AREA-1B | PARKING AREA |  | 1 | 169.7952 | 0.3 | 0.075 | 3.8204 | 169795.2
AREA-02 | PARKING AREA | CUM | 1 | 274.4526 |  | 0.1 | 27.4453 | 274452598.7
|  |  | 1 | 68.7105 |  | 0.1 | 6.8711 | 68710528.7
|  |  | 1 | 27.4953 |  | 0.1 | 2.7495 | 27495262.3
|  |  | 1 | 68.7093 |  | 0.1 | 6.8709 | 68709308
RA BILL-02
AREA-01 | MARKETING AREA OFFICE DROP OFF AREA |  | 1 | 408.4368 |  | 0.1 | 40.8437 | 408436776.7
| MEDIAN AREA DEDUCTION |  | -1 | 42.793 |  | 0.1 | -4.2793 | 42792993
AREA-02 | MARKETING OFFICE PEDESTRIAN PATHWAY |  | 1 | 110.9745 |  | 0.1 | 11.0975 | 110974537.5
AREA-03 | CAR PARKING PEDESTRIAN PATHWAY |  | 1 | 79.7488 |  | 0.1 | 7.9749 | 79748774
AREA-04 | MARKETING AREA OFFICE DROP OFF ENTRY GRANITE AREA |  | 1 | 99.9332 |  | 0.1 | 9.9933 | 99933168.5
AREA-05 | MARKETING OFFICE PEDESTRIAN PATHWAY-ENTRY |  | 1 | 29.4736 |  | 0.1 | 2.9474 | 29473632
|  |  | 1 | 35.474 |  | 0.1 | 3.5474 | 35474044.3
AREA-06 | CAR PARKING |  | 1 | 27.5 |  | 0.1 | 2.75 | 27500000
|  |  | 1 | 27.4953 |  | 0.1 | 2.7495 | 27495285.5
450MM KERB Below PCC
AREA-02 | MARKETING OFFICE AREA ENTRANCE |  | 1 | 51.8133 | 0.3 | 0.075 | 1.1658 | 51813.3
|  |  | 1 | 20.5444 | 0.3 | 0.075 | 0.46225 | 20544.4
AREA-03 | ROUND ABOUT AREA |  | 1 | 83.3172 | 0.3 | 0.075 | 1.8746 | 93317.2
AREA-04 | DRIVEWAY BESIDE WALKWAY |  | 1 | 132.9259 | 0.3 | 0.075 | 2.9908 | 132925.9
AREA-05 | DRIVEWAY BETWEEN PLANTER |  | 1 | 259.6208 | 0.3 | 0.075 | 5.8415 | 259620.8
AREA-06 | PARKING AREA KERB |  | 1 | 20.7902 | 0.3 | 0.075 | 0.46778 | 20790.2
|  |  | 1 | 56.0082 | 0.3 | 0.075 | 1.2602 | 56008.2
300MM KERB Below PCC
AREA-01 | MARKETING OFFICE AREA WALKWAY |  | 1 | 51.6025 | 0.3 | 0.075 | 1.1611 | 51602.5
|  |  | 1 | 49.1748 | 0.3 | 0.075 | 1.1064 | 49174.8
AREA-07 | PARKING AREA KERB |  | 1 | 44.2927 | 0.3 | 0.075 | 0.99659 | 44292.7
|  |  | 1 | 45.6837 | 0.3 | 0.075 | 1.0279 | 45683.7
AREA-08 | PARKING AREA KERB |  | 1 | 16.7563 | 0.3 | 0.075 | 0.37702 | 16756.3
|  |  | 1 | 16.6063 | 0.3 | 0.075 | 0.37364 | 16606.3
AREA-09 | DRIVEWAY BESIDE WALKWAY |  | 1 | 50.0412 | 0.3 | 0.075 | 1.1259 | 50041.2
|  |  | 1 | 50.1043 | 0.3 | 0.075 | 1.1273 | 50104.3
AREA-10 | MARKETING OFFICE AREA ENTRANCE |  | 1 | 59.8166 | 0.3 | 0.075 | 1.3459 | 59816.6
|  |  | 1 | 52.3787 | 0.3 | 0.075 | 1.1785 | 52378.7
AREA-11 | MARKETING OFFICE AREA ENTRANCE |  | 1 | 12.2146 | 0.3 | 0.075 | 0.27483 | 12214.6
|  |  | 1 | 12.5692 | 0.3 | 0.075 | 0.28281 | 12569.2
SAUCER DRAIN
AREA-01 | MARKETING OFFICE DROP OFF |  | 1 | 50.0706 | 0.3 | 0.1 | 1.5021 | 50070.6
|  |  | 1 | 18.7304 | 0.3 | 0.1 | 0.56191 | 18730.4
RA BILL-03
AREA-01 | MARKETING OFFICE WALKWAY |  | 1 | 94.1652 |  | 0.1 | 9.4165 | 94165172.4
AREA-02 | CARPARKING PEDESTRIAN WALKWAY |  | 1 | 50.0022 |  | 0.1 | 5.0002 | 50002229.2
AREA-03 | MAIN DRIVEWAY COBBLE STONE AREA |  | 1 | 120.75 | 1.5 | 0.1 | 18.1125 | 181171977
450MM KERB Below PCC
AREA-01 | DRIVEWAY NEAR ROUND ABOUT AREA |  | 1 | 9.79 | 0.3 | 0.075 | 0.22027 | 9790
AREA-03 | CARPARKING DRIVEWAY AREA |  | 1 | 49.9087 | 0.3 | 0.075 | 1.1229 | 49908.7
300MM KERB Below PCC
AREA-02 | CARPARKING PEDESTRIAN WALKWAY |  | 1 | 9.6129 | 0.3 | 0.075 | 0.21629 | 9612.9
|  |  | 1 | 7.6281 | 0.3 | 0.075 | 0.17163 | 7628.1
|  |  | 1 | 1.25 | 0.3 | 0.075 | 0.028125 | 1250
AREA-04 | MARKETING OFFICE NORTHSIDE WALKWAY |  | 1 | 79.5888 | 0.3 | 0.075 | 1.7907 | 79588.8
|  |  | 1 | 9.8824 | 0.3 | 0.075 | 0.22235 | 9882.4
|  |  | 1 | 66.7691 | 0.3 | 0.075 | 1.5023 | 66769.1
SAUCER DRAIN
AREA-01 | MAIN DRIVEWAY AREA |  | 1 | 120.3628 | 0.3 | 0.1 | 3.6109 | 120362.8
RA BILL-04
AREA-01 | MAIN DRIVEWAY COBBLE AREA |  | 1 | 20.25 | 1.5 | 0.1 | 3.0375 | 29508061.6
AREA-02 | MAIN DRIVEWAY COBBLE ENTRENCE AREA |  | 1 | 14.3 |  | 0.1 | 1.43 | 14300000
AREA-03 | NEAR MARKETING OFFICE PAVERS AREA |  | 1 | 54.4066 |  | 0.1 | 5.4407 | 54406601.4
| TOTAL | [5 empty] | 210.0148 | CUM | 199.389 | CUM
30 | Land__SUP/FILL_sweet earth fill Shifting and Filling of existing soil within the site for planter box and any other location manually with consolidation. | CUM
RA BILL-01
AREA-01 | PARKING AREA-PATHWAY |  | 1 | 352.1408 |  |  | 352.1408 | 352140810.1 | JMR-084
AREA-02 | PARKING PATHWAY-PLANTING AREA |  | 1 | 409.0159 |  | 0.498 | 203.6899 | 409015858.6 | JMR-084
AREA-03 | NEAR PARKING AREA |  | 1 | 329.6482 |  | 0.57 | 187.8995 | 329648194 | JMR-083
RA BILL-03
AREA-01 | MARKETING OFFICE SOUTHSIDE |  | 1 | 774.3015 |  | 0.24513 | 189.8006 | 774301468.3
AREA-02 | MARKETING OFFICE NORTHSIDE |  | 1 | 104.8237 |  | 0.24513 | 25.6949 | 104823717.5
AREA-03 | MARKETING AREA FRONT SIDE WALKWAY |  | 1 | 123.1996 |  | 0.375 | 46.1999 | 123199605.7
AREA-03 | MARKETING AREA FRONT SIDE WALKWAY |  | 1 | 36.8688 |  | 0.375 | 13.8258 | 36868782.6
AREA-04 | CARPARKING AREA PLANTER AREA |  | 1 | 54.8276 |  | 0.48712 | 26.7079 | 54827575.8
AREA-04 | CARPARKING AREA PLANTER AREA |  | 1 | 15.3291 |  | 0.48712 | 7.4672 | 15329071.1
AREA-04 | CARPARKING AREA PLANTER AREA |  | 1 | 12.5238 |  | 0.48712 | 6.1007 | 12523848.1
AREA-05 | ROUND ABOUT AREA |  | 1 | 13.5 | 12 | 0.84937 | 137.5987 | JMR-203
| RA BILL-04 | [9 empty] | -0.375
AREA-01 | MAIN DRIVEWAY CENTRE MEADIAN |  | 1 | 160.7173 |  | 0.375 | 60.269 | 160717283.8
AREA-06 | MAIN DRIVEWAY CENTRE MEADIAN |  | 1 | 43.1238 |  | 0.4 | 17.2495 | 43123819.5
AREA-02 | MAIN DRIVEWAY BESIDE PAVERS AREA |  | 0 | 100 | 2.2 | 0.1 | 0
AREA-03 | MAIN DRIVEWAY BESIDE PLANTER AREA |  | 0 | 100 | 1 | 0.38 | 0
AREA-04 | NEAR MARKETING OFFICE PAVERS AREA |  | 0 | 48.7222 |  | 0.2 | 0 | 48722230
AREA-05 | ROUNDABOUT INSIDE AREA |  | 1 | 692.6921 |  | 0.336 | 232.7445 | 692692082.4
| DEDUCTION OF FOUNTAIN |  | -1 | 229.0605 |  | 0.336 | -76.9643 | 229060513.6
RA BILL-05
AREA-03 | MAIN DRIVEWAY BESIDE PLANTER AREA |  | 1 | 100 | 1 | 0.375 | 37.5
AREA-02 | MAIN DRIVEWAY BESIDE PAVERS AREA |  | 1 | 100 | 2.2 | 0.1 | 22
AREA-04 | NEAR MARKETING OFFICE PAVERS AREA |  | 1 | 48.7222 |  | 0.2 | 9.7444 | 48722230
| TOTAL | [5 empty] | 1499.669 | CUM
20 | Land_SUP/FlX_Wet Mix Macadam Providing,laying 2 layers WMM (Wet mix macadem) with Stone aggregate with approved quality of 20mm down grade and quarry dust, well packed, correct to level. The surface shall be consolidated by 8 to 10 Tonne power road roller after spreading of well compacted earth or boulder soling as the sub base etc., complete. The finish consolidated thickness shall be 150mm.
RA BILL-01
AREA-01 | PARKING AREA | CUM | 1 | 795.4568 |  | 0.15 | 119.3185 | 795456777.4
RA BILL-02
AREA-01 | DRIVEWAY AREA |  | 1 | 1153.8229 |  | 0.15 | 173.0734 | 1153822865.2
AREA-02 | MARKETING OFFICE DROP OFF |  | 1 | 99.8273 |  | 0.15 | 14.9741 | 99827298.1
AREA-03 | MARKETING OFFICE DROP OFF |  | 1 | 408.4368 |  | 0.15 | 61.2655 | 408436776.7
| MEDIAN AREA DEDUCTION |  | -1 | 42.793 |  | 0.1 | -4.2793 | 42792993
RA BILL-03
AREA-01 | CARPARKING DRIVEWAY AREA |  | 1 | 216.521 |  | 0.15 | 32.4782 | 216521012
RA BILL-04
AREA-01 | MAIN DRIVEWAY AREA |  | 1 | 873.7941 |  | 0.15 | 131.0691 | 873794131.5
AREA-02 | ROUNDABOUT AREA |  | 1 | 335.1469 |  | 0.2 | 67.0294 | 335146877.1
AREA-03 | ROUNDABOUT AREA |  | 1 | 273.1111 |  | 0.2 | 54.6222 | 273111083.4
| TOTAL | [5 empty] | 649.5511 | CUM
130 | LAND_FIX_CONCRETE PAVERS Concrete Pavers Receving and fixing of Concrete Pavers blocks of 200 x 100 X 80mm. laid over 35mm thick cemen mortar 1:4 , joints to be cleaned, curing, cleaning, etc. to required line, level, etc. all complete cost including of all materials at site, necessary earth compaction, all labour charges and other charges required to complete. Color- Dark Grey. For Pedestrian walkway -80mm Thick Paver | SQM
RA BILL-02
AREA-03 | PARKING AREA WALKWAY-GREY |  | 1 | 352.111 |  |  | 352.111 | 352110965.2 | 352.111
| DEDUCTIONS |  | -1 | 31.5394 |  |  | -31.5394 | 31539406.1 | -31.5394
| GREY PAVER |  | 1 | 79.7488 |  |  | 79.7488 | 79748774 | 79.7488
AREA-04 | DRIVEWAY BESIDE PATHWAY-GREY |  | 1 | 101.7602 |  |  | 101.7602 | 101760213 | 101.7602
RA BILL-03
AREA-01 | MARKETING OFFICE FRONT SIDE |  | 1 | 123.3181 |  |  | 123.3181 | 123318142.2 | 123.3181 |  |  | 7774.5304 | 9501.08
|  |  | 1 | 35.3377 |  |  | 35.3377 | 35337655.7 | 35.3377
AREA-02 | CARPARKING PEDESTRIAN WALKWAY |  | 1 | 52.5217 |  |  | 52.5217 | 52521717.3 | 52.5217
RA BILL-04
AREA-01 | NEAR ROUNDABOUT AREA CORNER |  | 1 | 50.0577 |  |  | 50.0577 | 50057664
AREA-02 | MARKETING OFFICE NORTHSIDE PATHWAY |  | 0 | 117.1701 |  |  | 0 | 117170087.4 | NT
AREA-03 | MARKETING OFFICE AROUND PAVERS |  | 0 | 51.6 | 1.2 |  | 0 |  | NT
AREA-04 | MAIN DRIVEWAY BESIDE PATHWAY |  | 1 | 8.2538 |  |  | 8.2538 | 8253784.2
RA BILL-05
AREA-01 | PARKING AREA-LIGHT GREY |  | 1 | 429.8107 |  |  | 429.8107 | 429810721
| MEDIAN DEDUCTION |  | -1 | 42.7935 |  |  | -42.7935 | 42793454.3
AREA-02 | CAR PARKING AREA-DARK GREY |  | 1 | 274.9102 |  |  | 274.9102 | 274910206.7
|  |  | 1 | 221.433 |  |  | 221.433 | 221432999.2
AREA-02 | MARKETING OFFICE NORTHSIDE PATHWAY |  | 1 | 100.5697 |  |  | 100.5697 | 100569710.5 | NT
AREA-03 | MARKETING OFFICE AROUND PAVERS |  | 1 | 63.5683 | 1.2 |  | 63.57 | 63568266 | NT | 20083.7552
AREA-04 | DRIVEWAY EXIT SIDE PAVERS AREA |  | 1 | 19 | 1 |  | 19
| TOTAL | [5 empty] | 1838.0697 | M2 | 713.2581
100 | Receiving and laying controlled Reinforced Cement Concrete of M30 grade at all levels and heights specified below using ordinary Portland cement of grade 43 from approved manufacturer, river sand, 20mm and down size coarse aggregates, necessary admixtures approved by Consultants (Conplast SP-430SRV from Fosroc or equivalent), including all leads and lifts, pumping using line pump or boom placer, vibrating/compaction, scaffolding wherever necessary, all lead and lifts, tools & Plants, pumping the concrete to all levels, curing etc. complete but excluding cost of reinforcement and formwork, centering, shuttering. Depending on the size and location, the maximum depth of concreting will be decided by Engineer in casting at a time. | CUM
RA BILL-02
AREA-01 | CAR PARKING AREA |  | 0.483 | 299.7644 |  | 0.2 | 28.9572 | 299764425.8
RA BILL-03
AREA-01 | CAR PARKING AREA(HOLD QTY RA BILL-01) |  | 0.517 | 299.7644 |  | 0.2 | 30.9956 | 299764425.8
AREA-01 | MAIN DRIVEWAY 1 SIDE |  | 1 | 160 | 4.7 | 0.2 | 150.4 | 751644652.2
RA BILL-04
AREA-01 | MAIN DRIVEWAY 1 SIDE |  | 1 | 160 | 4.7 | 0.2 | 150.4 | 469504281
AREA-02 | ROUNDABOUT AREA |  | 1 | 335.1469 |  | 0.2 | 67.0294 | 335146877.1
| DEDUCTION OF COBBLE AREA |  | -1 | 8.0101 |  | 0.2 | -1.602 | 8010131.9
|  |  | -1 | 1.2051 |  | 0.2 | -0.24103 | 1205132
|  |  | -1 | 0.86387 |  | 0.2 | -0.17277 | 863868.3
|  |  | -1 | 6.9739 |  | 0.2 | -1.3948 | 6973889.3
|  |  | -1 | 0.90084 |  | 0.2 | -0.18017 | 900844.8
|  |  | -1 | 4.4952 |  | 0.2 | -0.89904 | 4495217.4
|  |  | -1 | 3.28 |  | 0.2 | -0.656 | 3279989.6
|  |  | -1 | 5.891 |  | 0.2 | -1.1782 | 5890957.3
|  |  | -1 | 7.5177 |  | 0.2 | -1.5035 | 7517703.2
|  |  | -1 | 4.6961 |  | 0.2 | -0.93923 | 4696141.6
|  |  | -1 | 2.3183 |  | 0.2 | -0.46365 | 2318274.4
|  |  | -1 | 4.4896 |  | 0.2 | -0.89791 | 4489566
|  |  | -1 | 2.5484 |  | 0.2 | -0.50968 | 2548396.5
AREA-03 | ROUNDABOUT AREA |  | 1 | 191.5747 |  | 0.2 | 38.3149 | 191574692.3
| DEDUCTION OF COBBLE AREA |  | -1 | 5.8687 |  | 0.2 | -1.1737 | 5868693.3
|  |  | -1 | 6.7479 |  | 0.2 | -1.3496 | 6747940.4
|  |  | -1 | 0.67741 |  | 0.2 | -0.13548 | 677411.8
|  |  | -1 | 3.457 |  | 0.2 | -0.69141 | 3457034.8
|  |  | -1 | 2.366 |  | 0.2 | -0.4732 | 2365996.1
|  |  | -1 | 3.4772 |  | 0.2 | -0.69543 | 3477165.9
|  |  | -1 | 1.989 |  | 0.2 | -0.3978 | 1989004.5
AREA-04 | CAR PARKING AREA DRIVEWAY |  | 1 | 215.1644 |  | 0.2 | 43.0329 | 215164361.2
AREA-05 | MAIN DRIVEWAY AREA |  | 1 | 4.8931 |  | 0.2 | 0.97862 | 4893120.4
RA BILL-05
AREA-01 | ROUNDABOUT AREA |  | 1 | 535.4468 |  | 0.2 | 107.0894 | 535446793.2
AREA-02 | CYCLE PARKING AREA |  | 1 | 4 | 12.6 | 0.2 | 10.08 | 85323125.8 | 50.4
|  |  | 1 | 4 | 2.7 | 0.2 | 2.16 |  | 10.8
|  |  | 1 | 5 | 2.8 | 0.2 | 2.8 |  | 14
| TOTAL | [5 empty] | 616.6834
50 | CHAMBER WORK (900*900* Depth up to 1.5mt) Excavation, Compaction, PCC Providing and laying 6 inch block masonry in cement mortar 1:3 (1 cement : 3 coarse sand) of in true line level and plumb for walls, with necessary scaffolding, curing etc., Providing, applying of External & internal plastering in c.m. 1:3, 15-20mm thick Single Coat including necessary scaffolding, as per design, curing and hacking to the surfaces & finish including chamber cover fixing on the top etc., complete. (Note: chamber cover supply by sattva). | NOS
RA BILL-02
HTP SOUTH SIDE
| 900*900 |  | 11 |  |  |  | 11
RA BILL-05
| CHAMBER WORK |  | 8 |  |  |  | 8
| TOTAL | [5 empty] | 19 | NOS
70 | CHAMBER WORK (600*600* Depth up to 01mt) Excavation, Compaction, PCC Providing and laying 6 inch block masonry in cement mortar 1:3 (1 cement : 3 coarse sand) of in true line level and plumb for walls, with necessary scaffolding, curing etc., Providing, applying of External & internal plastering in c.m. 1:3, 15-20mm thick Single Coat including necessary scaffolding, as per design, curing and hacking to the surfaces & finish and including chamber cover fixing on the top etc., complete. (Note: chamber cover supply by sattva) | NOS
RA BILL-02
BOREWELL AREA
| 600*600 |  | 2 |  |  |  | 2
RAK DG SIDE
| 600*600 |  | 2 |  |  |  | 2
| TOTAL | [5 empty] | 4 | NOS
80 | CHAMBER WORK (750*750* Depth up to 01mt) Excavation, Compaction, PCC Providing and laying 6 inch block masonry in cement mortar 1:3 (1 cement : 3 coarse sand) of in true line level and plumb for walls, with necessary scaffolding, curing etc., Providing, applying of External & internal plastering in c.m. 1:3, 15-20mm thick Single Coat including necessary scaffolding, as per design, curing and hacking to the surfaces & finish including chamber cover fixing on the top etc., complete. (Note: chamber cover supply by sattva) | NOS
RA BILL-02
MODULAR OFFICE
| 750*750 |  | 1 |  |  |  | 1
HTP SOUTH SIDE
| 750*750 |  | 2 |  |  |  | 2
MO ELECTRICAL ROOM
| 750*750 |  | 1 |  |  |  | 1
| TOTAL | [5 empty] | 4 | NOS
90 | CHAMBER WORK (300*300* Depth up to 0.1mt) Excavation, Compaction, PCC Providing and laying 6 inch block masonry in cement mortar 1:3 (1 cement : 3 coarse sand) of in true line level and plumb for walls, with necessary scaffolding, curing etc., Providing, applying of External & internal plastering in c.m. 1:3, 15-20mm thick Single Coat including necessary scaffolding, as per design, curing and hacking to the surfaces & finish including chamber cover fixing on the top etc., complete. (Note: chamber cover supply by sattva) | NOS
RA BILL-02
MODULAR OFFICE
| 300*300 |  | 1 |  |  |  | 1
MOCKUP BACKSIDE
| 300*300 |  | 4 |  |  |  | 4
INTERNAL COURTYARD
| 300*300 |  | 5 |  |  |  | 5
| 300*300-(JMR) |  | 2 |  |  |  | 2
RA BILL-05
| CHAMBER WORK |  | 18 |  |  |  | 18
| TOTAL | [5 empty] | 30 | NOS
30 | 55009582 LAND_SUP/FIX_GRANITE COBBLE HARDSCAPE WORKS Black flamed Granite Cobble Stone Providing & laying of Black Granite Cobble stones of 100X100mm over 50mm thick pcc bed to required shape, size and pattern .to required line, level, etc. all complete cost including of all materials at site, necessary earth compaction, all labour charges and other charges required to complete. Location - Driveway paving band (75mm thick) | SQM | [5 empty] | `
RA BILL-03
AREA-01 | DRIVEWAY SIDE PEDESTRIAN WALKWAY |  | 1 | 105 | 1.5 |  | 157.5
RA BILL-04
AREA-01 | MAIN DRIVEWAY 1 SIDE |  | 1 | 36 | 1.5 |  | 54
| TOTAL | [5 empty] | 211.5 | SQM
150 | LAND_POW ER TROWEL Power Trowel with broom finish for above item | M2 | [5 empty] | `
RA BILL-03
AREA -01 | MAIN DRIVEWAY 1 SIDE |  | 1 | 160 | 4.7 |  | 752 | 751644652.2
AREA -02 | CAR PARKING |  | 1 | 299.0585 |  |  | 299.0585 | 299058491.4
RA BILL-04
AREA-01 | MAIN DRIVEWAY 1 SIDE |  | 1 | 160 | 4.7 |  | 752 | 469504281 |  | 160 | 4.7
AREA-02 | ROUNDABOUT AREA |  | 1 | 335.1469 |  |  | 335.1469 | 335146877.1 |  | 335.1469
| DEDUCTION OF COBBLE AREA |  | -1 | 8.0101 |  |  | -8.0101 | 8010131.9 |  | 8.0101
|  |  | -1 | 1.2051 |  |  | -1.2051 | 1205132 |  | 1.2051
|  |  | -1 | 0.86387 |  |  | -0.86387 | 863868.3 |  | 0.86387
|  |  | -1 | 6.9739 |  |  | -6.9739 | 6973889.3 |  | 6.9739
|  |  | -1 | 0.90084 |  |  | -0.90084 | 900844.8 |  | 0.90084
|  |  | -1 | 4.4952 |  |  | -4.4952 | 4495217.4 |  | 4.4952
|  |  | -1 | 3.28 |  |  | -3.28 | 3279989.6 |  | 3.28
|  |  | -1 | 5.891 |  |  | -5.891 | 5890957.3 |  | 5.891
|  |  | -1 | 7.5177 |  |  | -7.5177 | 7517703.2 |  | 7.5177
|  |  | -1 | 4.6961 |  |  | -4.6961 | 4696141.6 |  | 4.6961
|  |  | -1 | 2.3183 |  |  | -2.3183 | 2318274.4 |  | 2.3183
|  |  | -1 | 4.4896 |  |  | -4.4896 | 4489566 |  | 4.4896
|  |  | -1 | 2.5484 |  |  | -2.5484 | 2548396.5 |  | 2.5484
AREA-03 | ROUNDABOUT AREA |  | 1 | 191.5747 |  |  | 191.5747 | 191574692.3 |  | 154.3199
| DEDUCTION OF COBBLE AREA |  | -1 | 5.8687 |  |  | -5.8687 | 5868693.3 |  | 5.8687 | 5868693.3
|  |  | -1 | 6.7479 |  |  | -6.7479 | 6747940.4 |  | 6.7479 | 6747940.4
|  |  | -1 | 0.67741 |  |  | -0.67741 | 677411.8 |  | 0.67741 | 677411.8
|  |  | -1 | 3.457 |  |  | -3.457 | 3457034.8 |  | 3.457 | 3457034.8
|  |  | -1 | 2.366 |  |  | -2.366 | 2365996.1 |  | 2.366 | 2365996.1
|  |  | -1 | 3.4772 |  |  | -3.4772 | 3477165.9 |  | 3.4772 | 3477165.9
|  |  | -1 | 1.989 |  |  | -1.989 | 1989004.5 |  | 1.989 | 1989004.5
AREA-04 | CAR PARKING AREA DRIVEWAY |  | 1 | 215.1644 |  |  | 215.1644 | 215164361.2
RA BILL-05
AREA-01 | ROUNDABOUT AREA |  | 1 | 535.4468 |  |  | 535.4468 | 535446793.2
AREA-02 | CYCLE PARKING AREA |  | 1 | 85.3231 |  |  | 85.3231 | 85323125.8
| TOTAL | [5 empty] | 3087.941 | SQM
160 | LAND_GROOVE CUTTING Groove cutting for above item | RMT
RA BILL-03
AREA-01 | MAIN DRIVWAY AREA |  | 24 | 4.7 |  |  | 112.8
AREA -02 | CAR PARKING |  | 1 | 50 |  |  | 50
|  |  | 8 | 6 |  |  | 48
RA BILL-04
AREA-01 | MAIN DRIVWAY AREA |  | 24 | 4.7 |  |  | 112.8
AREA-02 | CAR PARKING AREA EXTENSION |  | 1 | 6 |  |  | 6
|  |  | 6 | 4.7 |  |  | 28.2 | 6.49
| TOTAL | [5 empty] | 357.8 | RMT
10 | LAND_BASE PREPARATION BASE PREPARATION WORKS Clearing and grubbing of top 150mm top soil including cutting, removing and disposing of all materials such as trees, bushes, shrubs, stumps, roots, grass, weeds, top organic soil etc. complete.
AREA-05 | ROUND ABOUT AREA |  | 1 | 13.5 | 12 |  | 162 | JMR-203
RA BILL-04
AREA-01 | MARKETING OFFICE AROUND KERB EXCAVATION |  | 2 | 51.6 |  | 0.4 | 41.28
AREA-02 | MARKETING OFFICE AROUND KERB EXCAVATION |  | 1 | 81.1825 |  | 0.4 | 32.473 | 81182.5
AREA-02 | MARKETING OFFICE AROUND KERB EXCAVATION |  | 1 | 84.3358 |  | 0.4 | 33.7343 | 84335.8
| TOTAL | [5 empty] | 269.4873 | sqm

## BBS
BAR BENDING SCHEDULE RA BILL-05
REINFORCEMENT WORKS
Sl. No | TYPE | Description | SHAPE OF BAR |  |  |  | Dia | Spacing | No of Members | Nos of Bars | Lap Length | Cutting length(m) | 8mm | 10mm | 12mm | 16mm | 20mm | 25mm | 28mm | 32mm | TOTAL | Remarks
|  |  | L1 | L2 | L3 | Ld
AREA-01 |  | CAR PARKING AREA
| Slab | VERTICAL BARS |  |  |  |  | 8 | 0.225 | 1 | 223 |  | 5.95 | 1326.85 | [7 empty] | 1326.85
5.95
|  | HORIZONTAL BARS |  |  |  |  | 8 | 0.225 | 1 | 27 |  | 51.5 | 1390.5 | [7 empty] | 1390.5
|  |  |  | 49.9 |  | 1.6
RA BILL-03
AREA-01 |  | MAIN DRIVEWAY AREA
| Slab | VERTICAL BARS |  |  |  |  | 8 | 0.225 | 1 | 712 |  | 4.65 | 3310.8 | [7 empty] | 3310.8
4.65
|  | HORIZONTAL BARS |  |  |  |  | 8 | 0.225 | 1 | 22 |  | 165.15 | 3633.3 | [7 empty] | 3633.3
|  |  |  | 159.95 |  | 5.2
RA BILL-04
AREA-01 |  | MAIN DRIVEWAY AREA
| Slab | VERTICAL BARS |  |  |  |  | 8 | 0.225 | 1 | 712 |  | 4.65 | 3310.8 | [7 empty] | 3310.8
4.65
|  | HORIZONTAL BARS |  |  |  |  | 8 | 0.225 | 1 | 22 |  | 165.2 | 3634.4 | [7 empty] | 3634.4
|  |  |  | 160 |  | 5.2
AREA-02 |  | CARPARKING DRIVEWAY AREA
| Slab | VERTICAL BARS |  |  |  |  | 8 | 0.225 | 1 | 27 |  | 4.95 | 133.65 | [7 empty] | 133.65
4.95
|  | HORIZONTAL BARS |  |  |  |  | 8 | 0.225 | 1 | 23 |  | 5.95 | 136.85 | [7 empty] | 136.85
5.95
AREA-02 | Slab | VERTICAL BARS |  |  |  |  | 8 | 0.225 | 1 | 145 |  | 4.65 | 674.25 | [7 empty] | 674.25
4.65
|  | HORIZONTAL BARS |  |  |  |  | 8 | 0.225 | 1 | 22 |  | 33.2 | 730.4 | [7 empty] | 730.4
|  |  |  | 32.4 |  | 0.8
AREA-03 |  | MAIN DRIVEWAY ENTRY COBBLE AREA
| Slab | VERTICAL BARS |  |  |  |  | 8 | 0.15 | 1 | 11 |  | 4.65 | 51.15 | [7 empty] | 51.15
4.65
|  | HORIZONTAL BARS |  |  |  |  | 8 | 0.15 | 1 | 32 |  | 1.5 | 48 | [7 empty] | 48
1.5
RA BILL-05
AREA-01 |  | ROUND ABOUT AREA
|  | VERTICAL BARS |  |  |  |  | 8 | 0.225 | 1 | 629 |  | 6.5 | 4088.5 | [7 empty] | 4088.5
6.5
|  | VERTICAL BARS |  |  |  |  | 8 | 0.225 | 1 | 65.8889 |  | 5.69 | 374.9078 | [7 empty] | 374.9078
5.69
|  | VERTICAL BARS |  |  |  |  | 8 | 0.225 | 1 | 57.0889 |  | 3.45 | 196.9567 | [7 empty] | 196.9567
3.45
|  | VERTICAL BARS |  |  |  |  | 8 | 0.225 | 1 | 40.6 |  | 3.7 | 150.22 | [7 empty] | 150.22
3.7
|  | VERTICAL BARS |  |  |  |  | 8 | 0.225 | 1 | 65.8889 |  | 3.85 | 253.6722 | [7 empty] | 253.6722
3.85
|  | VERTICAL BARS |  |  |  |  | 8 | 0.225 | 1 | 65.4889 |  | 5.69 | 372.6318 | [7 empty] | 372.6318
5.69
|  | HORIZONTAL BARS |  |  |  |  | 8 | 0.225 | 1 | 1 |  | 5542.84 | 5542.84 | [7 empty] | 5542.84 | 455.8333
182.3333
72.0217
|  | TOTAL CUTTING LENGTH dia wise in mtr | [10 empty] | 29360.6784 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29360.6784
|  | Unit Weight | [10 empty] | 0.395 | 0.617 | 0.888 | 1.58 | 2.47 | 3.85 | 4.83 | 6.31
|  | Total (in KG) | [10 empty] | 11597.468 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11597.468
|  | Total (Diawise in MT) | [10 empty] | 11.5975 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11.5975
|  | Total quantity executed till date in kg | [10 empty] | 11597.468 | [8 empty] | KGS
|  | Total quantity executed till date in TONNES | [10 empty] | 11.5975 | [8 empty] | TONNES

## DC S
DCS AND ISSUE DETAILS
SL NO | DCNOS | DATE | DESCRIPTION | UNIT | QTY | REMARKS
1 | 657 | 2024-12-25 | GSB | 34980 | KG
2 | 658 | 2024-12-25 | GSB | 33800 | KG
3 | 659 | 2024-12-25 | GSB | 34450 | KG
4 | 660 | 2024-12-26 | GSB | 34370 | KG
5 | 661 | 2024-12-26 | GSB | 33950 | KG
6 | 665 | 2025-01-07 | GSB | 33960 | KG
7 | 666 | 2025-01-07 | GSB | 34460 | KG
8 | 667 | 2025-01-08 | GSB | 33450 | KG
9 | 698 | 2025-01-29 | GSB | 38220 | KG
10 | 685 | 2025-01-27 | GSB | 35220 | KG
11 | 687 | 2025-01-28 | GSB | 35150 | KG
12 | 688 | 2025-01-28 | GSB | 34530 | KG
13 | 689 | 2025-01-27 | GSB | 36060 | KG
14 | 690 | 2025-01-28 | GSB | 35915 | KG
15 | 691 | 2025-01-28 | GSB | 35514 | KG
16 | 692 | 2025-01-29 | GSB | 35550 | KG
17 | 693 | 2025-01-29 | GSB | 35100 | KG
18 | 694 | 2025-01-29 | GSB | 35150 | KG
19 | 695 | 2025-01-29 | GSB | 35400 | KG
20 | 696 | 2025-01-30 | GSB | 35960 | KG
21 | 697 | 2025-01-29 | GSB | 36540 | KG
22 | 557 | 2025-02-08 | GSB | 35650 | KG
23 | 556 | 2025-02-08 | GSB | 35990 | KG
24 | 555 | 2025-02-07 | GSB | 35500 | KG
25 | 554 | 2025-02-07 | GSB | 35970 | KG
26 | 553 | 2025-02-07 | GSB | 35750 | KG
27 | 552 | 2025-02-06 | GSB | 35910 | KG
RA BILL-02
28 | 563 | 2025-02-13 | GSB | 35890 | KG
29 | 571 | 2025-02-15 | GSB | 36110 | KG
30 | 591 | 2025-02-26 | GSB | 36800 | KG
31 | 592 | 2025-02-26 | GSB | 36800 | KG
32 | 593 | 2025-02-27 | GSB | 36800 | KG
33 | 600 | 2025-03-01 | GSB | 36800 | KG
34 | 202 | 2025-03-04 | GSB | 36800 | KG
35 | 205 | 2025-03-04 | GSB | 36300 | KG
36 | 206 | 2025-03-04 | GSB | 35610 | KG
37 | 207 | 2025-03-10 | GSB | 36800 | KG
38 | 208 | 2025-03-10 | GSB | 36650 | KG
39 | 209 | 2025-03-10 | GSB | 36250 | KG
40 | 210 | 2025-03-11 | GSB | 36950 | KG
41 | 211 | 2025-03-11 | GSB | 34900 | KG
42 | 212 | 2025-03-11 | GSB | 38740 | KG
43 | 213 | 2025-03-11 | GSB | 38640 | KG
44 | 216 | 2025-03-20 | GSB | 36800 | KG
45 | 217 | 2025-03-21 | GSB | 36800 | KG
46 | 218 | 2025-03-22 | GSB | 36800 | KG
47 | 219 | 2025-03-22 | GSB | 36800 | KG
48 | 222 | 2025-04-02 | GSB | 36800 | KG
49 | 223 | 2025-04-04 | GSB | 36800 | KG
50 | 224 | 2025-04-07 | GSB | 36800 | KG
51 | 225 | 2025-04-07 | GSB | 36800 | KG
52 | 226 | 2025-04-09 | GSB | 36800 | KG
53 | 228 | 2025-04-11 | GSB | 48200 | KG
54 | 233 | 2025-04-14 | GSB | 48210 | KG
55 | 234 | 2025-04-14 | GSB | 46420 | KG
56 | 235 | 2025-04-15 | GSB | 46710 | KG
57 | 245 | 2025-05-09 | GSB | 46800 | KG
58 | 246 | 2025-05-09 | GSB | 47910 | KG
59 | 707 | 2025-06-03 | GSB | 34480 | KG
60 | 709 | 2025-06-04 | GSB | 46840 | KG
61 | 710 | 2025-06-04 | GSB | 37100 | KG
2273209
|  |  |  | 1082.4805 | CUM
1 | 672 | 2025-01-21 | WET MIX | 32900 | KG
2 | 673 | 2025-01-22 | WET MIX | 34250 | KG
3 | 674 | 2025-01-22 | WET MIX | 35630 | KG
4 | 675 | 2025-01-22 | WET MIX | 36490 | KG
5 | 676 | 2025-01-23 | WET MIX | 36110 | KG
6 | 677 | 2025-01-23 | WET MIX | 35910 | KG
7 | 678 | 2025-01-23 | WET MIX | 35900 | KG
8 | 679 | 2025-01-23 | WET MIX | 36500 | KG
9 | 680 | 2025-01-23 | WET MIX | 36890 | KG
10 | 681 | 2025-01-23 | WET MIX | 38520 | KG
11 | 681 | 2025-01-24 | WET MIX | 36190 | KG
12 | 684 | 2025-01-25 | WET MIX | 36410 | KG
13 | 560 | 2025-02-09 | WET MIX | 35750 | KG
14 | 562 | 2025-02-12 | WET MIX | 35910 | KG
15 | 565 | 2025-02-14 | WET MIX | 35900 | KG
16 | 566 | 2025-02-14 | WET MIX | 35980 | KG
17 | 567 | 2025-02-14 | WET MIX | 36240 | KG
18 | 568 | 2025-02-14 | WET MIX | 36280 | KG
19 | 569 | 2025-02-14 | WET MIX | 36330 | KG
20 | 570 | 2025-02-14 | WET MIX | 36500 | KG
21 | 578 | 2025-02-21 | WET MIX | 35860 | KG
22 | 579 | 2025-02-21 | WET MIX | 37830 | KG
23 | 580 | 2025-02-21 | WET MIX | 33460 | KG
24 | 581 | 2025-02-21 | WET MIX | 34890 | KG
25 | 585 | 2025-02-22 | WET MIX | 46410 | KG
26 | 586 | 2025-02-23 | WET MIX | 43370 | KG
27 | 587 | 2025-02-23 | WET MIX | 36080 | KG
28 | 588 | 2025-02-23 | WET MIX | 46410 | KG
29 | 589 | 2025-02-23 | WET MIX | 46410 | KG
30 | 590 | 2025-02-24 | WET MIX | 34020 | KG
31 | 595 | 2025-02-27 | WET MIX | 46410 | KG
32 | 596 | 2025-02-27 | WET MIX | 46410 | KG
33 | 203 | 2025-03-04 | WET MIX | 46410 | KG
34 | 229 | 2025-04-11 | WET MIX | 48310 | KG
35 | 231 | 2025-04-14 | WET MIX | 46580 | KG
36 | 232 | 2025-04-14 | WET MIX | 34750 | KG
37 | 233 | 2025-04-14 | WET MIX | 48210 | KG
38 | 234 | 2025-04-14 | WET MIX | 46420 | KG
39 | 236 | 2025-04-22 | WET MIX | 48260 | KG
40 | 237 | 2025-04-22 | WET MIX | 38240 | KG
41 | 238 | 2025-04-22 | WET MIX | 38480 | KG
42 | 239 | 2025-04-23 | WET MIX | 38690 | KG
43 | 240 | 2025-05-06 | WET MIX | 46210 | KG
44 | 241 | 2025-05-06 | WET MIX | 38680 | KG
45 | 242 | 2025-05-07 | WET MIX | 36960 | KG
46 | 243 | 2025-05-07 | WET MIX | 34990 | KG
47 | 247 | 2025-05-09 | WET MIX | 48710 | KG
48 | 249 | 2025-05-15 | WET MIX | 47710 | KG
49 | 250 | 2025-05-15 | WET MIX | 48710 | KG
50 | 702 | 2025-05-15 | WET MIX | 48780 | KG
51 | 703 | 2025-05-15 | WET MIX | 46890 | KG
52 | 706 | 2025-06-03 | WET MIX | 37370 | KG
53 | 711 | 2025-06-05 | WET MIX | 37470 | KG
54 | 712 | 2025-06-06 | WET MIX | 37100 | KG
55 | 712 | 2025-06-06 | WET MIX | 38140 | KG
56 | 712 | 2025-06-06 | WET MIX | 38960 | KG
57 | 715 | 2025-07-04 | WET MIX | 36410 | KG
58 | 716 | 2025-07-05 | WET MIX | 37760 | KG
59 | 717 | 2025-07-12 | WET MIX | 35890 | KG
60 | 718 | 2025-07-12 | WET MIX | 37090 | KG
2376330
|  |  |  | 1080.15 | CUM
1 | 551 | 2025-02-01 | M SAND | 34200 | KG
2 | 654 | 2024-12-20 | M SAND | 32800 | KG
3 | 682 | 2025-01-23 | M SAND | 32750 | KG
4 | 564 | 2025-02-14 | M SAND | 35570 | KG
5 | 598 | 2025-02-28 | M SAND | 42270 | KG
6 | 599 | 2025-02-28 | M SAND | 42270 | KG
7 | 204 | 2025-03-04 | M SAND | 42270 | KG
8 | 214 | 2025-03-12 | M SAND | 34950 | KG
9 | 215 | 2025-03-18 | M SAND | 42270 | KG
10 | 221 | 2025-03-29 | M SAND | 42270 | KG
11 | 230 | 2025-04-13 | M SAND | 46410 | KG
12 | 248 | 2025-05-09 | M SAND | 49290 | KG
13 | 708 | 2025-06-03 | M SAND | 36340 | KG
14 | 714 | 2025-07-04 | M SAND | 34620 | KG
548280
|  |  |  | 304.6 | CUM
1 | 655 | 2024-12-20 | 20MM JELLY | 32100 | KG
2 | 700 | 2025-02-01 | 20MM JELLY | 33140 | KG
65240
|  |  |  | 40.775 | CUM
1 | 699 | 2025-01-30 | CEMENT | 50 | BAGS
2 | 671 | 2025-01-20 | CEMENT | 50 | BAGS
3 | 558 | 2025-02-08 | CEMENT | 100 | BAGS
4 | 583 | 2025-02-22 | CEMENT | 100 | BAGS
|  |  |  | 300 | BAGS
1 | 656 | 2024-12-20 | 4" SOLID BLOCK | 700 | NOS
2 | 670 | 2025-01-20 | 6" BLOCK | 300 | NOS
3 | 669 | 2025-01-19 | 6" BLOCK | 300 | NOS
4 | 561 | 2025-02-11 | 6" BLOCK | 500 | NOS
|  |  |  | 1800 | NOS

## NT (hidden)
NON-TENDERED ITEMS
MEASUREMENT BACK UP
SL.NO | DESCRIPTION | UNIT | NOS | L | B | D | QTY | REMARKS
NT-01 | SAUCER DRAIN | RMT
RA BILL-02
AREA-01 | MARKETING OFFICE DROP OFF |  | 1 | 50.0706 |  |  | 50.0706 | 50070.6
|  |  | 1 | 18.7304 |  |  | 18.7304 | 18730.4
RA BILL-03
AREA-01 | MAIN DRIVEWAY AREA |  | 1 | 120.011 |  |  | 120.011 | 120011
RA BILL-04
AREA-01 | MAIN DRIVEWAY AREA |  | 1 | 40.0109 |  |  | 40.0109 | 40010.9
RA BILL-04
AREA-01 | MAIN DRIVEWAY AREA |  | 1 | 40.0109 |  |  | 40.0109 | 40010.9
AREA-02 | ROUNDABOUT AREA |  | 1 | 22.815 |  |  | 22.815 | 22815
AREA-03 | ROUNDABOUT AREA |  | 1 | 15.8189 |  |  | 15.8189 | 15818.9
| S | [5 empty] | 307.4677 | RMT
SL.NO | DESCRIPTION | UNIT | NOS | L | B | D | QTY | REMARKS
NT-02 | 40MM THICK STEEL GREY FLAMED FINISH GRANITE FLOORING | SQM
RA BILL-02
AREA-01 | MARKETING OFFICE DROP OFF |  | 1 | 99.9151 |  |  | 99.9151 | 99915139.8
| MODULE OFFICE FRONT SIDE |  | 1
| TOTAL | [5 empty] | 99.9151 | SQM
SL.NO | DESCRIPTION | UNIT | NOS | L | B | D | QTY | REMARKS
NT-03 | LDPE SHEET 600 MICRON BELOW M30 CONCRETE | SQM
RA BILL-02
AREA-01 | CAR PARKING AREA |  | 1 | 299.7644 |  |  | 299.7644 | 299764425.8
RA BILL-03
RA BILL-04
AREA-01 | MAIN DRIVEWAY 1 SIDE |  | 1 | 160 | 4.7 |  | 752
AREA-02 | ROUNDABOUT AREA |  | 1 | 335.1469 |  |  | 335.1469 | 335146877.1
| DEDUCTION OF COBBLE AREA |  | -1 | 8.0101 |  |  | -8.0101 | 8010131.9
|  |  | -1 | 1.2051 |  |  | -1.2051 | 1205132
|  |  | -1 | 0.86387 |  |  | -0.86387 | 863868.3
|  |  | -1 | 6.9739 |  |  | -6.9739 | 6973889.3
|  |  | -1 | 0.90084 |  |  | -0.90084 | 900844.8
|  |  | -1 | 4.4952 |  |  | -4.4952 | 4495217.4
|  |  | -1 | 3.28 |  |  | -3.28 | 3279989.6
|  |  | -1 | 5.891 |  |  | -5.891 | 5890957.3
|  |  | -1 | 7.5177 |  |  | -7.5177 | 7517703.2
|  |  | -1 | 4.6961 |  |  | -4.6961 | 4696141.6
|  |  | -1 | 2.3183 |  |  | -2.3183 | 2318274.4
|  |  | -1 | 4.4896 |  |  | -4.4896 | 4489566
|  |  | -1 | 2.5484 |  |  | -2.5484 | 2548396.5
AREA-03 | ROUNDABOUT AREA |  | 1 | 273.1111 |  |  | 273.1111 | 273111083.4
| DEDUCTION OF COBBLE AREA |  | -1 | 5.8687 |  |  | -5.8687 | 5868693.3
|  |  | -1 | 6.7479 |  |  | -6.7479 | 6747940.4
|  |  | -1 | 3.457 |  |  | -3.457 | 3457034.8
|  |  | -1 | 2.366 |  |  | -2.366 | 2365996.1
|  |  | -1 | 5.4874 |  |  | -5.4874 | 5487377.5
|  |  | -1 | 6.6297 |  |  | -6.6297 | 6629714.1
|  |  | -1 | 2.8848 |  |  | -2.8848 | 2884835.1
|  |  | -1 | 3.6484 |  |  | -3.6484 | 3648357.5
|  |  | -1 | 0.67741 |  |  | -0.67741 | 677411.8
AREA-04 | CAR PARKING AREA DRIVEWAY |  | 1 | 215.1644 |  |  | 215.1644 | 215164361.2
AREA-01 | MAIN DRIVEWAY AREA |  | 1 | 160 | 4.7 |  | 752
| TOTAL | [5 empty] | 2536.2293 | SQM
NT-04 | LAND_FIX_CONCRETE PAVERS Concrete Pavers Receving and fixing of Concrete Pavers blocks of 200 x 100 X 80mm. laid over 35mm thick cemen mortar 1:4 , joints to be cleaned, curing, cleaning, etc. to required line, level, etc. all complete cost including of all materials at site, necessary earth compaction, all labour charges and other charges required to complete. Color- Dark Grey. ForPARKING AREA -80mm Thick Paver | [9 empty] | 1834.36
RA BILL-02
AREA-01 | PARKING AREA-LIGHT GREY |  | 1 | 429.8107 |  |  | 429.8107 | 429810721 | 429.8107
| MEDIAN DEDUCTION |  | -1 | 42.7935 |  |  | -42.7935 | 42793454.3 | -42.7935
AREA-02 | CAR PARKING AREA-DARK GREY |  | 1 | 274.9102 |  |  | 274.9102 | 274910206.7 |  | 274.9102
|  |  | 1 | 221.433 |  |  | 221.433 | 221432999.2 |  | 221.433
| TOTAL | [5 empty] | 883.3605 | SQM

## DCS (hidden)
DCS AND ISSUE DETAILS
SL NO | DCNOS | DATE | DESCRIPTION | UNIT | QTY | REMARKS
1 | 657 | 2024-12-25 | GSB | 34980 | KG
2 | 658 | 2024-12-25 | GSB | 33800 | KG
3 | 659 | 2024-12-25 | GSB | 34450 | KG
4 | 660 | 2024-12-26 | GSB | 34370 | KG
5 | 661 | 2024-12-26 | GSB | 33950 | KG
6 | 665 | 2025-01-07 | GSB | 33960 | KG
7 | 666 | 2025-01-07 | GSB | 34460 | KG
8 | 667 | 2025-01-08 | GSB | 33450 | KG
9 | 698 | 2025-01-29 | GSB | 38220 | KG
10 | 685 | 2025-01-27 | GSB | 35220 | KG
11 | 687 | 2025-01-28 | GSB | 35150 | KG
12 | 688 | 2025-01-28 | GSB | 34530 | KG
13 | 689 | 2025-01-27 | GSB | 36060 | KG
14 | 690 | 2025-01-28 | GSB | 35915 | KG
15 | 691 | 2025-01-28 | GSB | 35514 | KG
16 | 692 | 2025-01-29 | GSB | 35550 | KG
17 | 693 | 2025-01-29 | GSB | 35100 | KG
18 | 694 | 2025-01-29 | GSB | 35150 | KG
19 | 695 | 2025-01-29 | GSB | 35400 | KG
20 | 696 | 2025-01-30 | GSB | 35960 | KG
21 | 697 | 2025-01-29 | GSB | 36540 | KG
22 | 557 | 2025-02-08 | GSB | 35650 | KG
23 | 556 | 2025-02-08 | GSB | 35990 | KG
24 | 555 | 2025-02-07 | GSB | 35500 | KG
25 | 554 | 2025-02-07 | GSB | 35970 | KG
26 | 553 | 2025-02-07 | GSB | 35750 | KG
27 | 552 | 2025-02-06 | GSB | 35910 | KG
RA BILL-02
28 | 563 | 2025-02-13 | GSB | 35890 | KG
29 | 571 | 2025-02-15 | GSB | 36110 | KG
30 | 591 | 2025-02-26 | GSB | 36800 | KG
31 | 592 | 2025-02-26 | GSB | 36800 | KG
32 | 593 | 2025-02-27 | GSB | 36800 | KG
33 | 600 | 2025-03-01 | GSB | 36800 | KG
34 | 202 | 2025-03-04 | GSB | 36800 | KG
35 | 205 | 2025-03-04 | GSB | 36300 | KG
36 | 206 | 2025-03-04 | GSB | 35610 | KG
37 | 207 | 2025-03-10 | GSB | 36800 | KG
38 | 208 | 2025-03-10 | GSB | 36650 | KG
39 | 209 | 2025-03-10 | GSB | 36250 | KG
40 | 210 | 2025-03-11 | GSB | 36950 | KG
41 | 211 | 2025-03-11 | GSB | 34900 | KG
42 | 212 | 2025-03-11 | GSB | 38740 | KG
43 | 213 | 2025-03-11 | GSB | 38640 | KG
44 | 216 | 2025-03-20 | GSB | 36800 | KG
45 | 217 | 2025-03-21 | GSB | 36800 | KG
46 | 218 | 2025-03-22 | GSB | 36800 | KG
47 | 219 | 2025-03-22 | GSB | 36800 | KG
48 | 222 | 2025-04-02 | GSB | 36800 | KG
49 | 223 | 2025-04-04 | GSB | 36800 | KG
50 | 224 | 2025-04-07 | GSB | 36800 | KG
51 | 225 | 2025-04-07 | GSB | 36800 | KG
52 | 226 | 2025-04-09 | GSB | 36800 | KG
53 | 228 | 2025-04-11 | GSB | 48200 | KG
54 | 233 | 2025-04-14 | GSB | 48210 | KG
55 | 234 | 2025-04-14 | GSB | 46420 | KG
56 | 235 | 2025-04-15 | GSB | 46710 | KG
57 | 245 | 2025-05-09 | GSB | 46800 | KG
58 | 246 | 2025-05-09 | GSB | 47910 | KG
59 | 707 | 2025-06-03 | GSB | 34480 | KG
60 | 709 | 2025-06-04 | GSB | 46840 | KG
61 | 710 | 2025-06-04 | GSB | 37100 | KG
2273209
|  |  |  | 1082.4805 | CUM
1 | 672 | 2025-01-21 | WET MIX | 32900 | KG
2 | 673 | 2025-01-22 | WET MIX | 34250 | KG
3 | 674 | 2025-01-22 | WET MIX | 35630 | KG
4 | 675 | 2025-01-22 | WET MIX | 36490 | KG
5 | 676 | 2025-01-23 | WET MIX | 36110 | KG
6 | 677 | 2025-01-23 | WET MIX | 35910 | KG
7 | 678 | 2025-01-23 | WET MIX | 35900 | KG
8 | 679 | 2025-01-23 | WET MIX | 36500 | KG
9 | 680 | 2025-01-23 | WET MIX | 36890 | KG
10 | 681 | 2025-01-23 | WET MIX | 38520 | KG
11 | 681 | 2025-01-24 | WET MIX | 36190 | KG
12 | 684 | 2025-01-25 | WET MIX | 36410 | KG
13 | 560 | 2025-02-09 | WET MIX | 35750 | KG
14 | 562 | 2025-02-12 | WET MIX | 35910 | KG
15 | 565 | 2025-02-14 | WET MIX | 35900 | KG
16 | 566 | 2025-02-14 | WET MIX | 35980 | KG
17 | 567 | 2025-02-14 | WET MIX | 36240 | KG
18 | 568 | 2025-02-14 | WET MIX | 36280 | KG
19 | 569 | 2025-02-14 | WET MIX | 36330 | KG
20 | 570 | 2025-02-14 | WET MIX | 36500 | KG
21 | 578 | 2025-02-21 | WET MIX | 35860 | KG
22 | 579 | 2025-02-21 | WET MIX | 37830 | KG
23 | 580 | 2025-02-21 | WET MIX | 33460 | KG
24 | 581 | 2025-02-21 | WET MIX | 34890 | KG
25 | 585 | 2025-02-22 | WET MIX | 46410 | KG
26 | 586 | 2025-02-23 | WET MIX | 43370 | KG
27 | 587 | 2025-02-23 | WET MIX | 36080 | KG
28 | 588 | 2025-02-23 | WET MIX | 46410 | KG
29 | 589 | 2025-02-23 | WET MIX | 46410 | KG
30 | 590 | 2025-02-24 | WET MIX | 34020 | KG
31 | 595 | 2025-02-27 | WET MIX | 46410 | KG
32 | 596 | 2025-02-27 | WET MIX | 46410 | KG
33 | 203 | 2025-03-04 | WET MIX | 46410 | KG
34 | 229 | 2025-04-11 | WET MIX | 48310 | KG
35 | 231 | 2025-04-14 | WET MIX | 46580 | KG
36 | 232 | 2025-04-14 | WET MIX | 34750 | KG
37 | 233 | 2025-04-14 | WET MIX | 48210 | KG
38 | 234 | 2025-04-14 | WET MIX | 46420 | KG
39 | 236 | 2025-04-22 | WET MIX | 48260 | KG
40 | 237 | 2025-04-22 | WET MIX | 38240 | KG
41 | 238 | 2025-04-22 | WET MIX | 38480 | KG
42 | 239 | 2025-04-23 | WET MIX | 38690 | KG
43 | 240 | 2025-05-06 | WET MIX | 46210 | KG
44 | 241 | 2025-05-06 | WET MIX | 38680 | KG
45 | 242 | 2025-05-07 | WET MIX | 36960 | KG
46 | 243 | 2025-05-07 | WET MIX | 34990 | KG
47 | 247 | 2025-05-09 | WET MIX | 48710 | KG
48 | 249 | 2025-05-15 | WET MIX | 47710 | KG
49 | 250 | 2025-05-15 | WET MIX | 48710 | KG
50 | 702 | 2025-05-15 | WET MIX | 48780 | KG
51 | 703 | 2025-05-15 | WET MIX | 46890 | KG
52 | 706 | 2025-06-03 | WET MIX | 37370 | KG
53 | 711 | 2025-06-05 | WET MIX | 37470 | KG
54 | 712 | 2025-06-06 | WET MIX | 37100 | KG
55 | 712 | 2025-06-06 | WET MIX | 38140 | KG
56 | 712 | 2025-06-06 | WET MIX | 38960 | KG
2229180
|  |  |  | 1013.2636 | CUM
1 | 551 | 2025-02-01 | M SAND | 34200 | KG
2 | 654 | 2024-12-20 | M SAND | 32800 | KG
3 | 682 | 2025-01-23 | M SAND | 32750 | KG
4 | 564 | 2025-02-14 | M SAND | 35570 | KG
5 | 598 | 2025-02-28 | M SAND | 42270 | KG
6 | 599 | 2025-02-28 | M SAND | 42270 | KG
7 | 204 | 2025-03-04 | M SAND | 42270 | KG
8 | 214 | 2025-03-12 | M SAND | 34950 | KG
9 | 215 | 2025-03-18 | M SAND | 42270 | KG
10 | 221 | 2025-03-29 | M SAND | 42270 | KG
11 | 230 | 2025-04-13 | M SAND | 46410 | KG
12 | 248 | 2025-05-09 | M SAND | 49290 | KG
13 | 708 | 2025-06-03 | M SAND | 36340 | KG
513660
|  |  |  | 285.3667 | CUM
1 | 655 | 2024-12-20 | 20MM JELLY | 32100 | KG
2 | 700 | 2025-02-01 | 20MM JELLY | 33140 | KG
65240
|  |  |  | 40.775 | CUM
1 | 699 | 2025-01-30 | CEMENT | 50 | BAGS
2 | 671 | 2025-01-20 | CEMENT | 50 | BAGS
3 | 558 | 2025-02-08 | CEMENT | 100 | BAGS
4 | 583 | 2025-02-22 | CEMENT | 100 | BAGS
|  |  |  | 300 | BAGS
1 | 656 | 2024-12-20 | 4" SOLID BLOCK | 700 | NOS
2 | 670 | 2025-01-20 | 6" BLOCK | 300 | NOS
3 | 669 | 2025-01-19 | 6" BLOCK | 300 | NOS
4 | 561 | 2025-02-11 | 6" BLOCK | 500 | NOS
|  |  |  | 1800 | NOS

## ISSUE DETAILS
DCS AND ISSUE DETAILS
SL NO | DC/ ISSUE SLIPS | DATE | DESCRIPTION | UNIT | QTY |  | INVOICE NO | REMARKS
KERB STONE
1 | 069 | 2024-12-20 | KERB STONE 600*450*100MM | NOS | 360 |  | 2830 | FULL BATTER
2 | 069 | 2024-12-20 | KERB STONE 600*450*100MM | NOS | 252 |  | 2829 | FULL BATTER
3 | 070 | 2024-12-21 | KERB STONE 600*450*100MM | NOS | 52 |  | 2847 | FULL BATTER
4 | 070 | 2024-12-21 | KERB STONE 600*450*100MM | NOS | 156 | 820 | 2845 | FULL BATTER
1 | 004 | 2025-01-24 | KERB STONE 600*300*100 MM | NOS | 334 |  | 3277 | FLUSH
2 | 078 | 2024-12-23 | KERB STONE 600*300*100 MM | NOS | 335 |  | 2947 | FLUSH
3 | 021 | 2024-02-12 | KERB STONE 600*300*100 MM | NOS | 608 |  | 3532 | FLUSH
4 | 021 | 2024-02-12 | KERB STONE 600*300*100 MM | NOS | 528 |  | 3531 | FLUSH |  | 114
5 | 028 | 2025-02-17 | KERB STONE 600*300*100 MM | NOS | 576 |  | 3599 | FLUSH | 576 | 20352
6 | 028 | 2025-02-17 | KERB STONE 600*300*100 MM | NOS | 512 |  | 3597 | FLUSH |  | 5352
10 | 051 | 2025-03-03 | KERB STONE 600*300*100 MM | NOS | 480 |  | 3772 | FLUSH
10 | 052 | 2025-03-03 | KERB STONE 600*300*100 MM | NOS | 287 |  | 3773 | FLUSH
3660
1 | 100 | 2025-01-20 | KERB STONE 600*450*150 MM | NOS | 348 |  | 3230 | FULL BATTER
2 | 100 | 2025-01-20 | KERB STONE 600*450*150 MM | NOS | 354 |  | 3231 | FULL BATTER
3 | 034 | 2025-02-19 | KERB STONE 600*450*150 MM | NOS | 48 |  | 3614 | FULL BATTER
4 | 035 | 2025-02-18 | KERB STONE 600*450*150 MM | NOS | 300 |  | 3613
5 | 028 | 2025-02-17 | KERB STONE 600*450*150 MM | NOS | 216 |  | 3598
6 | 041 | 2025-02-21 | KERB STONE 600*450*150 MM | NOS | 67 |  | 3648
8 | 035 | 2025-02-18 | KERB STONE 600*300*100 MM | NOS | 216 |  | 3611 | FLUSH
9 | 035 | 2025-02-18 | KERB STONE 600*300*100 MM | NOS | 180 |  | 3612 | FLUSH
1729
SAUCER DRAIN
1 | 100 | 2025-01-20 | SAUCER DRAIN 600*300*125 MM | NOS | 420 |  | 3229
2 | 100 | 2025-01-20 | SAUCER DRAIN 600*300*125 MM | NOS | 280 |  | 3228
3 | 078 | 2024-12-28 | SAUCER DRAIN 600*300*125 MM | NOS | 259 |  | 2948
4 | 034 | 2025-02-19 | SAUCER DRAIN 600*300*125 MM | NOS | 320 |  | 3615
5 | 034 | 2025-02-19 | SAUCER DRAIN 600*300*150 MM | NOS | 75 |  | 3614
8 | 072 | 2024-12-23 | SAUCER DRAIN 600*300*125 MM | NOS | 441 |  | 2874
11 | 064 | 2025-03-13 | SAUCER DRAIN 600*300*150 MM | NOS | 189 |  | 3917
12 | 064 | 2025-03-13 | SAUCER DRAIN 600*300*150 MM | NOS | 172 |  | 3916
13 | 051 | 2025-03-03 | SAUCER DRAIN 600*300*150 MM | NOS | 280 |  | 3774
14 | 052 | 2025-03-03 | SAUCER DRAIN 600*300*125 MM | NOS | 28 |  | 3775
15 | 054 | 2025-03-03 | SAUCER DRAIN 600*300*150 MM | NOS | 210 |  | 3783
2674
CONCRETE PAVERS
1 | 070 | 2024-12-21 | CONCRETE PAVERS LIGHT GREY-100*200*60MM | SQFT | 1419 |  | 2847
3 | 042 | 2025-02-21 | CONCRETE PAVERS LIGHT GREY-100*200*60MM | SQFT | 1677 |  | 3649
4 | 034 | 2025-02-19 | CONCRETE PAVERS LIGHT GREY-100*200*60MM | SQFT | 1806 |  | 3623
5 | 040 | 2025-05-13 | CONCRETE PAVERS LIGHT GREY-100*200*60MM | SQFT | 1817 |  |  |  | 0
8 | 078 | 2025-12-27 | CONCRETE PAVERS LIGHT GREY-100*200*60MM | SQFT | 475 |  | 2947
7 | 054 | 2025-03-03 | CONCRETE PAVERS LIGHT GREY-100*200*60MM | SQFT | 2189 | 9383 | 2780 | 872.026
1 | 004 | 2025-01-24 | CONCRETE PAVERS DARK GREY-100*200*80MM | SQFT | 413.33 |  | 3277
2 | 004 | 2025-01-24 | CONCRETE PAVERS DARK GREY-100*200*80MM | SQFT | 1567.24 |  | 3278
3 | 072 | 2024-12-23 | CONCRETE PAVERS DARK GREY-100*200*80MM | SQFT | 1981 |  | 2873
4 | 042 | 2025-02-21 | CONCRETE PAVERS BLACK-100*200*80MM | SQFT | 516 |  | 3650
6 | 053 | 2025-03-03 | CONCRETE PAVERS BLACK-100*200*80MM | SQFT | 1858 |  | 3782
7 | 053 | 2025-03-03 | CONCRETE PAVERS BLACK-100*200*80MM | SQFT | 1445 |  | 3781
9 | 054 | 2025-03-03 | CONCRETE PAVERS BLACK-100*200*80MM | SQFT | 826 | 8606.57 | 3784 | 799.8671
GRANITE
1 | 083 | 2025-01-07 | GRANITE SADARAHALLI ANTIQUE-18MM THICK | SQFT | 287.81 | 26.7481
2 | 083 | 2025-01-07 | GRANITE SADARAHALLI ANTIQUE-30MM THICK | SQFT | 57.81 | 5.3727
3 | 083 | 2025-01-07 | GRAITE JET BLACK POLISH 50MM THICK | SQFT | 503.03 | 46.75
4 | 040 | 2025-02-21 | GRAITE JET BLACK POLISH 40MM THICK | SQFT | 521.805 | 48.4949
5 | 066 | 2024-12-18 | GRAITE JET BLACK POLISH 40MM THICK | SQFT | 645.613 | 60.0012 | 183
6 | 066 | 2025-02-21 | GRAITE JET BLACK POLISH 30MM THICK | SQFT | 83.87 | 7.7946 | 183
7 | 074 | 2024-12-26 | STEEL GREY GRANITE SLAB | SQFT | 66.9 | 6.2175 | 188
8 | 074 | 2024-12-26 | STEEL GREY GRANITE 40 MM | SQFT | 646.18 | 60.0539 | 188
CONCRETE
1 | 7791 | 2025-02-08 | RMC-M10 | CUM | 7 |  | IS NO-039
2 | 7801 | 2025-02-09 | RMC-M10 | CUM | 8
3 | 7792 | 2025-02-08 | RMC-M10 | CUM | 8
4 | 7879 | 2025-02-12 | RMC-M10 | CUM | 7
5 | 7881 | 2025-02-12 | RMC-M10 | CUM | 5
6 | 7877 | 2025-02-12 | RMC-M10 | CUM | 8
7 | 8334 | 2025-02-24 | RMC-M10 | CUM | 6
8 | 8338 | 2025-02-24 | RMC-M10 | CUM | 6
9 | 8362 | 2025-02-25 | RMC-M10 | CUM | 8
10 | 8430 | 2025-02-27 | RMC-M10 | CUM | 6
11 | 8431 | 2025-02-27 | RMC-M10 | CUM | 7
12 | 8432 | 2025-02-27 | RMC-M10 | CUM | 7
13 | 8433 | 2025-02-27 | RMC-M10 | CUM | 7
14 | 8334 | 2025-02-27 | RMC-M10 | CUM | 7
15 | 8509 | 2025-03-01 | RMC-M10 | CUM | 6
16 | 8516 | 2025-03-01 | RMC-M10 | CUM | 5
17 | 8581 | 2025-03-04 | RMC-M10 | CUM | 6
18 | 8821 | 2025-03-13 | RMC-M10 | CUM | 3
19 | 9063 | 2025-03-20 | RMC-M10 | CUM | 5
20 | 9065 | 2025-03-20 | RMC-M10 | CUM | 3
21 | 9141 | 2025-03-22 | RMC-M10 | CUM | 3
22 | 157742 | 2025-03-08 | RMC-M10 | CUM | 5
23 | 157763 | 2025-03-08 | RMC-M10 | CUM | 5
24 | 9378 | 2025-03-28 | RMC-M10 | CUM | 3
25 | 22 | 2025-04-01 | RMC-M10 | CUM | 3
26 | 230 | 2025-04-06 | RMC-M10 | CUM | 5
27 | 556 | 2025-04-14 | RMC-M10 | CUM | 5
28 | 235 | 2025-04-17 | RMC-M10 | CUM | 3
29 | 675 | 2025-04-18 | RMC-M10 | CUM | 3
30 | 786 | 2025-04-22 | RMC-M10 | CUM | 3
31 | 804 | 2025-04-23 | RMC-M10 | CUM | 3
32 | 825 | 2025-04-24 | RMC-M10 | CUM | 3
33 | 1088 | 2025-06-04 | RMC-M10 | CUM | 3
34 | 1182 | 2025-05-06 | RMC-M10 | CUM | 3
35 | 1153 | 2025-05-06 | RMC-M10 | CUM | 4
28 | 006 | 2025-06-05 | RMC-M10 | CUM | 3 |  | 105
29 | 004 | 2025-05-27 | RMC-M10 | CUM | 13 |  | 73
30 | 013 | 2025-06-27 | RMC-M10 | CUM | 6 |  | 134
201
1 | 015 | 2025-02-04 | STEEL 8MM DIA | MT | 28.86 | 28.86
1 | 065 | 2025-03-17 | OPC 43 GRADE CEMENT | BAGS | 300
[6 empty] | 300 | YECD1010794
CONCRETE
1 | 018 | 2025-04-22 | RMC-M30 | CUM | 98 |  | 23
2 | 078 | 2025-03-26 | RMC-M30 | CUM | 80 |  | 664
3 | 078 |  |  | CUM | 38
4 | 006 | 2025-06-05 | RMC-M30 | CUM | 117 |  | 105
5 | 004 | 2025-05-27 | RMC-M30 | CUM | 70 |  | 73
6 | 012 | 2025-06-19 | RMC-M30 | CUM | 55 |  | 118
7 | 016 | 2025-07-03 | RMC-M30 | CUM | 52 | 510 | 144

## RECON
RECONCILATION SUMMARY -RA BILL-05 & FINAL
SL. No | NAME OF MATERIAL | UNIT | RECEIVED QTY | CONSUMED QTY (As per RA Bill-04) | Co-efficient | WORK IN PROGRESS | STOCK AT SITE | Returned to Sattva | GATEWAY RECIVED | DIFFERENCE QTY | PERCENTAGE OF WASTAGE | REMARKS
1 | KERB STONE
| KERB STONE 600*300*100 MM FLUSH | NOS | 3660 | 1910 | 1.6393 |  |  | 270 | 1350 | 130 | 3.552%
| KERB STONE 600*450*150 MM F/B | NOS | 2549 | 1817 | 1.6393 |  |  |  | 1300 | -568 | -22.28%
2 | SAUCER DRAIN | [8 empty] | 0
| SAUCER DRAIN 600*300*125 MM | NOS | 2674 | 439 | 1.6393 |  |  | 950 | 600 | 685 | 25.62%
0
3 | CONCRETE PAVERS | SQM | 1671.8931 | 1836.4197 |  | 0 |  |  |  | -164.5266 | -9.841%
| CONCRETE PAVERS LIGHT GREY-100*200*60MM | SQM | 872.026 | 1064.8502 | [5 empty] | -192.8242 | -22.11%
| CONCRETE PAVERS DARK GREY-100*200*80MM | SQM | 799.8671 | 771.5695 | [5 empty] | 28.2976 | 3.538%
4 | GRANITE | [5 empty] | 0
| GRANITE SADARAHALLI ANTIQUE-30MM THICK | SQM | 5.3707 | [6 empty] | 5.3707 | 100% | NOT USED IN SITE
| GRAITE JET BLACK POLISH 50MM THICK | SQM | 46.128 | [6 empty] | 46.128 | 100% | NOT USED IN SITE
| STEEL GREY GRANITE, FLAMED 40MM THK | SQM | 120.054 | 99.9151 | [5 empty] | 20.1389 | 16.77%
| STEEL GREY GRANITE, ANTIQUE FINISH- 30MM | SQM | 14.011 | [6 empty] | 14.011 | 100% | NOT USED IN SITE
| SADARAHALLI ANTIQUE GRANITE 20MM THK | SQM | 26.228 | [6 empty] | 26.228 | 100% | NOT USED IN SITE
| JET BLACK GRANITE POLISHED, 40MM THK | SQM | 108.5 | [6 empty] | 108.5 | 100% | NOT USED IN SITE
| JET BLACK GRANITE POLISHED, 20MM THK | SQM | 42 | [6 empty] | 42 | 100% | NOT USED IN SITE
5 | CONCRETE | [8 empty] | 0
| RMC-M30 | CUM | 617 | 602.9942 | [5 empty] | 14.0058 | 2.27%
| RMC-M10 | CUM | 196 | 199.389 | [5 empty] | -3.389 | -1.729%
6 | STEEL | [8 empty] | 0
| 8MM DIA STEEL | MT | 28.86 | 11.5975 |  |  |  | 9.57 | 4.2 | 3.4925 | 12.1%

## RLS
LEVELS DETAILS |  |  |  |  | LEVELS DETAILS
SL NO. | RL | FFL | REMARKS |  | SL NO. | RL | FFL | REMARKS
CAR PARKING PLANTATION AREA
1 | 97.56 | 98.055 |  |  | 1 | 97.3 | 98.1
2 | 97.509 | 98.1 |  |  | 2 | 97.54 | 98.05
3 | 97.706 | 98.13 |  |  | 3 | 97.824 | 98.07
4 | 97.548 | 98.105 |  |  | 4 | 97.391 | 98.14
5 | 97.493 | 98.04 |  |  | 5 | 97.764 | 98.08
6 | 97.558 | 98.155 |  |  | 6 | 95.65 | 98.01
7 | 97.561 | 98.015 |  |  | 7 | 98.79 | 98.145
8 | 97.617 | 98.115 |  |  | 8 | 97.721 | 98.105
9 | 97.532 | 98.15 |  |  | 9 | 97.745
10 | 97.543 | 98.085 |  |  | 10 | 97.234
11 | 97.486 | 98.075 |  |  | 11 | 97.65
12 | 97.718 | 97.89 |  |  | AVL LEVELS | 97.5099 | 98.0875
13 | 97.682 | 98.085 |  |  | DEPTH |  | 0.57759 | M
14 | 97.755 | 98.15
15 | 97.64 | 98.075
16 | 97.484 | 98.04
17 | 97.51 | 98.105
| 1658.902 | 1667.37
AVL LEVELS | 97.5825 | 98.0806
DEPTH |  | 0.49812 | M
|  | RA BILL 03 |  |  |  | RA BILL 03
| LEVELS DETAILS |  |  |  | LEVELS DETAILS
| SL NO. | RL | FFL | REMARKS | SL NO. | RL | FFL | REMARKS
| MARKETING OFFICE SOUTH SIDE |  |  |  | CARPARKING AREA SOIL FILLING
| 1 | 97.684 | 97.975 |  | 1 | 97.637 | 98.21
| 2 | 97.722 | 97.97 |  | 2 | 97.859 | 98.215
| 3 | 97.778 | 97.96 |  | 3 | 97.718 | 98.215
| 4 |  | 97.99 |  | 4 | 97.628 | 98.19
| 5 |  | 97.965 |  | 5 | 97.682 | 98.175
| 6 |  | 97.96 |  | 6 | 97.682 | 98.18
| 7 |  | 97.975 |  | 7 |  | 98.205
| 8 |  | 97.99 |  | 8 |  | 98.115
|  | 293.184 | 783.785 |  |  | 586.206 | 785.505
| AVL LEVELS | 97.728 | 97.9731 |  | AVL LEVELS | 97.701 | 98.1881
| DEPTH |  | 0.24513 | M | DEPTH |  | 0.48712 | M
|  | RA BILL 03 |  |  |  | RA BILL 03
| LEVELS DETAILS |  |  |  | LEVELS DETAILS
| SL NO. | RL | FFL | REMARKS | SL NO. | RL | FFL | REMARKS
| ELECTRIC SHED DEMOLITION LEVELS |  |  |  | MARKETING OFFICE FRONT SIDE PLANTER AREA
| 1 | 96.575 | 97.675 |  | 1 | 97.6 | 97.975
| 2 | 96.34 | 97.66 |  |  | 97.6 | 97.975
| 3 | 96.775 | 97.75 |  | AVL LEVELS | 97.6 | 97.975
| 4 | 96.8 | 97.75 |  | DEPTH |  | 0.375 | M
| 5 | 96.9 | 97.66
| 6 | 97.17 | 97.665
| 7 | 97.07 | 97.67
| 8 | 97.07 | 97.665
|  | 774.7 | 781.495
| AVL LEVELS | 96.8375 | 97.6869
| DEPTH |  | 0.84937 | M
| RA BILL 04 |  |  |  | RA BILL 04
| LEVELS DETAILS |  |  |  | LEVELS DETAILS
| SL NO. | RL | FFL | REMARKS | SL NO. | RL | FFL | REMARKS
| DRIVEWAY CENTRE MEDIAN PLANTER BOX |  |  |  | ROUNDABOUT INSIDE FILLING AREA
| 1 | 96.9 | 97.3 |  | 1 | 97.51 | 98.05
|  | 96.9 | 97.3 |  | 2 | 97.66 | 98.02
| AVL LEVELS | 96.9 | 97.3 |  | 3 | 97.48 | 98.025
| DEPTH |  | 0.4 | M | 4 | 97.54 | 97.93
[5 empty] | 5 | 97.56 | 97.835
[5 empty] | 6 | 97.55 | 97.9
[5 empty] | 7 | 97.93 | 97.82
| RA BILL 04 |  |  |  |  | 683.23 | 685.58
| LEVELS DETAILS |  |  |  | AVL LEVELS | 97.6043 | 97.94
[5 empty] | DEPTH |  | 0.33571 | M
| SL NO. | RL | FFL | REMARKS
DRIVEWAY BESIDE PLANTER BOX
| 1 | 97.6 | 97.975
|  | 97.6 | 97.975
| AVL LEVELS | 97.6 | 97.975
| DEPTH |  | 0.375 | M

## ISSUE BACKUP (hidden)
DCS AND ISSUE DETAILS
SL NO | DC/ ISSUE SLIPS | DATE | DESCRIPTION | UNIT | QTY |  | REMARKS
KERB STONE
1 | 069 | 2024-12-20 | KERB STONE 600*450*100MM | NOS | 360 |  | 2830 | FULL BATTER
2 | 069 | 2024-12-20 | KERB STONE 600*450*100MM | NOS | 252 |  | 2829 | FULL BATTER
3 | 070 | 2024-12-21 | KERB STONE 600*450*100MM | NOS | 52 |  | 2847 | FULL BATTER
4 | 070 | 2024-12-21 | KERB STONE 600*450*100MM | NOS | 156 |  | 2845 | FULL BATTER
5 | 070 | 2024-12-21 | KERB STONE 600*450*100MM | NOS | 360 |  | 2830 | FULL BATTER
5 | 041 | 2025-02-21 | KERB STONE 600*450*100MM | NOS | 67 | 1247 | 3648 | FULL BATTER
1 | 004 | 2025-01-24 | KERB STONE 600*300*100 MM | NOS | 334 |  | 3277 | FLUSH
2 | 078 | 2024-12-23 | KERB STONE 600*300*100 MM | NOS | 335 |  | 2947 | FLUSH
3 | 021 | 2024-02-12 | KERB STONE 600*300*100 MM | NOS | 608 |  | 3532 | FLUSH
4 | 021 | 2024-02-12 | KERB STONE 600*300*100 MM | NOS | 528 |  | 3531 | FLUSH
5 | 028 | 2025-02-17 | KERB STONE 600*300*100 MM | NOS | 576 |  | 3599 | FLUSH
6 | 028 | 2025-02-17 | KERB STONE 600*300*100 MM | NOS | 512 | 2893 | 3597 | FLUSH
1 | 100 | 2025-01-20 | KERB STONE 600*450*150 MM | NOS | 348 |  | 3230 | FULL BATTER
2 | 100 | 2025-01-20 | KERB STONE 600*450*150 MM | NOS | 340 |  | ` | FULL BATTER
3 | 034 | 2025-02-19 | KERB STONE 600*450*150 MM | NOS | 48 |  |  | FULL BATTER
4 | 035 | 2025-02-18 | KERB STONE 600*450*150 MM | NOS | 300
5 | 41 | 2025-02-21 | KERB STONE 600*450*150 MM | NOS | 227 | 1263 | 3648
SAUCER DRAIN
1 | 100 | 2025-01-20 | SAUCER DRAIN 600*300*125 MM | NOS | 405 |  | 3229
2 | 100 | 2025-01-20 | SAUCER DRAIN 600*300*125 MM | NOS | 275 |  | 3228
3 | 078 | 2024-12-28 | SAUCER DRAIN 600*300*125 MM | NOS | 259 |  | 2948
4 | 034 | 2025-02-19 | SAUCER DRAIN 600*300*125 MM | NOS | 320
5 | 034 | 2025-02-19 | SAUCER DRAIN 600*300*150 MM | NOS | 75
6 | 035 | 2025-02-18 | SAUCER DRAIN 600*300*150 MM | NOS | 216 |  | 3611
7 | 035 | 2025-02-18 | SAUCER DRAIN 600*300*150 MM | NOS | 180 |  | 3612
8 | 072 | 2024-12-23 | SAUCER DRAIN 600*300*125 MM | NOS | 441 |  | 2874
9 | 041 | 2025-02-21 | SAUCER DRAIN 600*300*125 MM | NOS | 42 |  | 3648
10 | 028 | 2025-02-17 | SAUCER DRAIN 600*300*150 MM | NOS | 216
11 | 064 | 2025-03-13 | SAUCER DRAIN 600*300*150 MM | NOS | 189
12 | 064 | 2025-03-13 | SAUCER DRAIN 600*300*150 MM | NOS | 172 | 2790 | 3598
CONCRETE PAVERS
1 | 070 | 2024-12-21 | CONCRETE PAVERS LIGHT GREY-100*200*60MM | SQFT | 1419 |  | 2847
2 | 078 | 2024-12-28 | CONCRETE PAVERS LIGHT GREY-100*200*60MM | SQFT | 475 |  | 2947
3 | 042 | 2025-02-21 | CONCRETE PAVERS LIGHT GREY-100*200*60MM | SQFT | 1677 |  | 3649
4 | 034 | 2025-02-19 | CONCRETE PAVERS LIGHT GREY-100*200*60MM | SQFT | 1806 |  | 3623
5 | 040 | 2025-05-13 | CONCRETE PAVERS LIGHT GREY-100*200*60MM | SQFT | 1817
6 | 040 | 2025-05-13 | CONCRETE PAVERS LIGHT GREY-100*200*60MM | SQFT | 1817
7 |  |  | CONCRETE PAVERS LIGHT GREY-100*200*60MM | SQFT | 2188.8 | 11199.8
1 | 004 | 2025-01-24 | CONCRETE PAVERS DARK GREY-100*200*80MM | SQFT | 413.33 |  | 3277
2 | 004 | 2025-01-24 | CONCRETE PAVERS DARK GREY-100*200*80MM | SQFT | 1567.24 |  | 3278
3 | 072 | 2024-12-23 | CONCRETE PAVERS DARK GREY-100*200*80MM | SQFT | 1981 |  | 2873
4 | 042 | 2025-02-21 | CONCRETE PAVERS BLACK-100*200*80MM | SQFT | 516
5 | 064 | 2025-03-13 | CONCRETE PAVERS BLACK-100*200*80MM | SQFT | 850 |  | 3650
6 | 053 | 2025-03-03 | CONCRETE PAVERS BLACK-100*200*80MM | SQFT | 1858 |  | 3782
7 | 053 | 2025-03-03 | CONCRETE PAVERS BLACK-100*200*80MM | SQFT | 1445 |  | 3781
8 | 054 | 2025-03-03 | CONCRETE PAVERS BLACK-100*200*80MM | SQFT | 826 | 9456.57 | 3781
GRANITE
1 | 083 | 2025-01-07 | GRANITE SADARAHALLI ANTIQUE-18MM THICK | SQFT | 287.81 | 287.81
2 | 083 | 2025-01-07 | GRANITE SADARAHALLI ANTIQUE-30MM THICK | SQFT | 57.81 | 57.81
3 | 083 | 2025-01-07 | GRAITE JET BLACK POLISH 50MM THICK | SQFT | 503.03 | 503.03
CONCRETE
1 | 7791 | 2025-02-08 | RMC-M10 | CUM | 7 |  | IS NO-039
2 | 7801 | 2025-02-09 | RMC-M10 | CUM | 8
3 | 7792 | 2025-02-08 | RMC-M10 | CUM | 8
4 | 7879 | 2025-02-12 | RMC-M10 | CUM | 7
5 | 7881 | 2025-02-12 | RMC-M10 | CUM | 5
6 | 7877 | 2025-02-12 | RMC-M10 | CUM | 8
7 | 8334 | 2025-02-24 | RMC-M10 | CUM | 6
8 | 8338 | 2025-02-24 | RMC-M10 | CUM | 6
9 | 8362 | 2025-02-25 | RMC-M10 | CUM | 8
10 | 8430 | 2025-02-27 | RMC-M10 | CUM | 6
11 | 8431 | 2025-02-27 | RMC-M10 | CUM | 7
12 | 8432 | 2025-02-27 | RMC-M10 | CUM | 7
13 | 8433 | 2025-02-27 | RMC-M10 | CUM | 7
14 | 8334 | 2025-02-27 | RMC-M10 | CUM | 7
15 | 8509 | 2025-03-01 | RMC-M10 | CUM | 6
16 | 8516 | 2025-03-01 | RMC-M10 | CUM | 5
17 | 8581 | 2025-03-04 | RMC-M10 | CUM | 6
18 | 8821 | 2025-03-13 | RMC-M10 | CUM | 3
19 | 9063 | 2025-03-20 | RMC-M10 | CUM | 5
20 | 9065 | 2025-03-20 | RMC-M10 | CUM | 3
21 | 9141 | 2025-03-22 | RMC-M10 | CUM | 3
22 | 157742 | 2025-03-08 | RMC-M10 | CUM | 5
23 | 157763 | 2025-03-08 | RMC-M10 | CUM | 5
24 | 9378 | 2025-03-28 | RMC-M10 | CUM | 3
25 | 22 | 2025-04-01 | RMC-M10 | CUM | 3
26 | 230 | 2025-04-06 | RMC-M10 | CUM | 5
27 | 556 | 2025-04-14 | RMC-M10 | CUM | 5
28 | 235 | 2025-04-17 | RMC-M10 | CUM | 3
29 | 675 | 2025-04-18 | RMC-M10 | CUM | 3
30 | 786 | 2025-04-22 | RMC-M10 | CUM | 3
31 | 804 | 2025-04-23 | RMC-M10 | CUM | 3
32 | 825 | 2025-04-24 | RMC-M10 | CUM | 3
33 | 1088 | 2025-06-04 | RMC-M10 | CUM | 3
34 | 1182 | 2025-05-06 | RMC-M10 | CUM | 3
35 | 1153 | 2025-05-06 | RMC-M10 | CUM | 4
28 | 006 | 2025-06-05 | RMC-M10 | CUM | 3 |  | 105
29 | 004 | 2025-05-27 | RMC-M10 | CUM | 13 |  | 73
30 | 013 | 2025-06-27 | RMC-M10 | CUM | 6 |  | 134
201
1 | 015 | 2025-02-04 | STEEL 8MM DIA | MT | 28.86 | 28.86
1 | 065 | 2025-03-17 | OPC 43 GRADE CEMENT | BAGS | 300
[6 empty] | 300 | YECD1010794
CONCRETE
1 | 018 | 2025-04-22 | RMC-M30 | CUM | 98 |  | 23
2 | 078 | 2025-03-26 | RMC-M30 | CUM | 80 |  | 664
3 | 078 |  |  | CUM | 38
4 | 006 | 2025-06-05 | RMC-M30 | CUM | 117 |  | 105
5 | 004 | 2025-05-27 | RMC-M30 | CUM | 70 |  | 73
6 | 012 | 2025-06-19 | RMC-M30 | CUM | 55 |  | 118
7 | 016 | 2025-07-03 | RMC-M30 | CUM | 52 | 510 | 144

## Recovery details
RMC Issued details - Pragathi Landscapers LLP
Sl.No | Description | Unit | Grade | Qty | Rate | Amount Excluding Tax | Remarks
1 | Feb'24 | Cum | M10 | 43 | 3018 | 129774 | Rate Reference : UNO Infracon PO No: 4000071141
2 | March'24 | Cum | M10 | 54 | 3018 | 162972
3 | 01.04.2025 to 06.05.2025 | Cum | M10 | 82 | 3018 | 247476
4 | 07.05.2025 to 04.07.2025 | Cum | M10 | 12 | 3018 | 36216 | NO concrete in this period
| Total |  |  |  |  | 576438
Cement Issued details - Pragathi Landscapers LLP
Sl.No | Description | Unit | Grade | Qty | Rate | Amount Including Tax | Remarks
1 | Cement | MT | 43 | 15 | 5800 | 87000
| Total |  |  |  |  | 87000

## Hold Amount Details
RMC Hold details - Pragathi Landscapers LLP
Sl.No | Description | Unit | Issue Qty | Certified Qty | Difference in Qty | Rate | Amount Excluding Tax | Remarks
1 | RMC M30 GARDE | Cum | #REF! | #REF! | #REF! | 3570 | #REF! | Rate Reference : UNO Infracon PO No: 4000073577
| Total | [5 empty] | #REF!
Snag Point Hold details - Pragathi Landscapers LLP
Sl.No | Description |  | Bill Vaule | % of Amount Hold for Snag Points not Cleared | Amount Excluding Tax | Remarks
1 | RA Bill 03 |  | 1592229.7286 | 10% | 159223 | 10% Hold Amt due to Snag Point not yet Clear
| Total |  |  |  | 159223

## Pragathi RMC Details
SATTVA SUPPLY RMC DETAILS /RASK - SATTVA CITY
SATTVA SUPPLY RMC DETAILS/ PRAGATHI
DATE | SUPPLER | DC NO | UNIT | M10 | M25 | M30 | TOTAL QTY.
08.02.2025 | UNO | 7791 | M3 | 7 |  |  | 7
08.02.2025 | UNO | 7792 | M3 | 8 |  |  | 8
09.02.2025 | UNO | 7801 | M3 | 8 |  |  | 8
12.02.2025 | UNO | 7877 | M3 | 8 |  |  | 8
12.02.2025 | UNO | 7879 | M3 | 7 |  |  | 7
12.02.2025 | UNO | 7881 | M3 | 5 |  |  | 5
MANTH OF FEB.1ST HALF |  |  |  | 43 | 0 | 0 | 43
24.02.2025 | UNO | 8334 | M3 | 6 |  |  | 6
24.02.2025 | UNO | 8338 | M3 | 6 |  |  | 6
25.02.2025 | UNO | 8362 | M3 | 8 |  |  | 8
27.02.2025 | UNO | 8430 | M3 | 6 |  |  | 6
27.02.2025 | UNO | 8431 | M3 | 7 |  |  | 7
27.02.2025 | UNO | 8432 | M3 | 7 |  |  | 7
27.02.2025 | UNO | 8433 | M3 | 7 |  |  | 7
27.02.2025 | UNO | 8334 | M3 | 7 |  |  | 7
MANTH OF FEB.2ST HALF |  |  |  | 54 |  |  | 54
01.03.2025 | UNO | 8509 | M3 | 6 |  |  | 6
01.03.2025 | UNO | 8516 | M3 | 5 |  |  | 5
04.03.2025 | UNO | 8581 | M3 | 6 |  |  | 6
13.03.2025 | UNO | 8821 | M3 | 3 |  |  | 3
18.03.2025 | UNO | 8957 | M3 |  |  | 7 | 7
18.03.2025 | UNO | 9860 | M3 |  |  | 7 | 7
18.03.2025 | UNO | 8966 | M3 |  |  | 7 | 7
18.03.2025 | UNO | 8970 | M3 |  |  | 8 | 8
20.03.2025 | UNO | 9063 | M3 | 5 |  |  | 5
20.03.2025 | UNO | 9065 | M3 | 3 |  |  | 3 |  | 401
22.03.2025 | UNO | 9141 | M3 | 3 |  |  | 3
25.03.2025 | UNO | 9247 | M3 |  |  | 7 | 7
25.03.2025 | UNO | 9249 | M3 |  |  | 7 | 7
25.03.2025 | UNO | 9250 | M3 |  |  | 7 | 7
25.03.2025 | UNO | 9253 | M3 |  |  | 7 | 7
25.03.2025 | UNO | 9255 | M3 |  |  | 7 | 7
25.03.2025 | UNO | 9256 | M3 |  |  | 7 | 7
25.03.2025 | UNO | 9266 | M3 |  |  | 8 | 8
25.03.2025 | UNO | 9270 | M3 |  |  | 1 | 1
08.03.2025 | HELLA | 157742 | M3 | 5 |  |  | 5
08.03.2025 | HELLA | 157763 | M3 | 5 |  |  | 5
MANTH OF MARCH |  |  |  | 41 | 0 | 80 | 121
28.03.2025 | uno | 9378 | m3 | 3 |  |  | 3
01.04.2025 | uno | 22 | m3 | 3 |  |  | 3
02.04.2025 | uno | 88 | m3 |  |  | 7 | 7
02.04.2025 | uno | 89 | m3 |  |  | 7 | 7
02.04.2025 | uno | 91 | m3 |  |  | 5 | 5
02.04.2025 | uno | 95 | m3 |  |  | 1 | 1
04.04.2025 | uno | 146 | m3 |  |  | 7 | 7
04.04.2025 | uno | 147 | m3 |  |  | 7 | 7
04.04.2025 | uno | 148 | m3 |  |  | 7 | 7
06.04.2025 | uno | 230 | m3 | 5 |  |  | 5
08.04.2025 | uno | 306 | m3 |  |  | 7 | 7
08.04.2025 | uno | 307 | m3 |  |  | 7 | 7
08.04.2025 | uno | 308 | m3 |  |  | 6 | 6
08.04.2025 | uno | 314 | m3 |  |  | 6 | 6
08.04.2025 | uno | 316 | m3 |  |  | 6 | 6
08.04.2025 | uno | 317 | m3 |  |  | 6 | 6
08.04.2025 | uno | 323 | m3 |  |  | 6 | 6
08.04.2025 | uno | 325 | m3 |  |  | 7 | 7
08.04.2025 | uno | 326 | m3 |  |  | 6 | 6
14.04.2025 | uno | 556 | m3 | 5 |  |  | 5
manth of april 1ts half |  |  |  | 16 | 0 | 98 | 114
17.04.2025 | uno | 235 | M3 | 3 |  |  | 3
18.04.2025 | uno | 675 | M3 | 3 |  |  | 3
22.04.2025 | uno | 786 | M3 | 3 |  |  | 3
23.04.2025 | uno | 804 | M3 | 3 |  |  | 3
24.04.2025 | uno | 825 | M3 | 3 |  |  | 3
25.04.2025 | uno | 840 | M3 |  |  | 6 | 6
25.04.2025 | uno | 841 | M3 |  |  | 6 | 6
25.04.2025 | uno | 842 | M3 |  |  | 7 | 7 | 25
25.04.2025 | uno | 844 | M3 |  |  | 7 | 7 | 22
25.04.2025 | uno | 845 | M3 |  |  | 6 | 6 | TOTAL 47 CUM
25.04.2025 | uno | 849 | M3 |  |  | 6 | 6
manth of april 2st half |  |  |  | 15 | 0 | 38 | 53
04.05.2025 | UNO | 1088 | M3 | 3
06.05.2025 | UNO | 1182 | M3 | 3
06.05.2025 | UNO | 1153 | M3 | 4
10.05.2025 | UNO | 1293 | M3 |  |  | 7
10.05.2025 | UNO | 1298 | M3 |  |  | 7
10.05.2025 | UNO | 1303 | M3 |  |  | 7
10.05.2025 | UNO | 1312 | M3 |  |  | 7
11.05.2025 | UNO | 1351 | M3 |  |  | 7
11.05.2025 | UNO | 1353 | M3 |  |  | 7
11.05.2025 | UNO | 1357 | M3 |  |  | 7
11.05.2026 | UNO | 1359 | M3 |  |  | 7
11.05.2027 | UNO | 1361 | M3 |  |  | 7
11.05.2028 | UNO | 1363 | M3 |  |  | 7
13.05.2025 | UNO | 1394 | M3 | 3
Month of may 1st half |  |  |  | 13 | 0 | 70 | 0
23.05.2025 | UNO | 1698 | M3 | 3 |  |  | 3
26.05.2025 | UNO | 1756 | M3 |  |  | 6 | 6
26.05.2025 | UNO | 1757 | M3 |  |  | 8 | 8
26.05.2025 | UNO | 1763 | M3 |  |  | 3 | 3
26.05.2025 | UNO | 1767 | M3 |  |  | 7 | 7
26.05.2025 | UNO | 1769 | M3 |  |  | 6 | 6
26.05.2025 | UNO | 1771 | M3 |  |  | 7 | 7
26.05.2025 | UNO | 1780 | M3 |  |  | 6 | 6
26.05.2025 | UNO | 1781 | M3 |  |  | 7 | 7
26.05.2025 | UNO | 1782 | M3 |  |  | 7 | 7
30.05.2025 | UNO | 1944 | M3 |  |  | 7 | 7
30.05.2025 | UNO | 1945 | M3 |  |  | 7 | 7
30.05.2025 | UNO | 1946 | M3 |  |  | 7 | 7
30.05.2025 | UNO | 1947 | M3 |  |  | 7 | 7
30.05.2025 | UNO | 1948 | M3 |  |  | 6 | 6
30.05.2025 | UNO | 1949 | M3 |  |  | 6 | 6
30.05.2025 | UNO | 1950 | M3 |  |  | 7 | 7
30.05.2025 | UNO | 1951 | M3 |  |  | 7 | 7
30.05.2025 | UNO | 1952 | M3 |  |  | 6 | 6
MANTH OF MAY 2 HALF |  |  |  | 3 | 0 | 117 | 120
08.06.2025 | UNO | 2224 | M3 |  |  | 6 | 6
08.06.2025 | UNO | 2228 | M3 |  |  | 6 | 6
08.06.2025 | UNO | 2229 | M3 |  |  | 7 | 7
08.06.2025 | UNO | 2233 | M3 |  |  | 7 | 7
08.06.2025 | UNO | 2234 | M3 |  |  | 7 | 7
08.06.2025 | UNO | 2237 | M3 |  |  | 7 | 7
08.06.2025 | UNO | 2242 | M3 |  |  | 6 | 6
08.06.2025 | UNO | 2243 | M3 |  |  | 6 | 6
08.06.2025 | UNO | 2247 | M3 |  |  | 3 | 3
05.06.2025 | UNO | 2170 | M3 | 3 |  |  | 3
05.06.2025 | UNO | 2183 | M3 | 3 |  |  | 3
manth of jun 1st half |  |  |  | 6 | 0 | 55 | 61
26.06.2025 | UNO | 2751 | M3 |  |  | 6 | 6
26.06.2025 | UNO | 2752 | M3 |  |  | 7 | 7
26.06.2025 | UNO | 2756 | M3 |  |  | 7 | 7
26.06.2025 | UNO | 2757 | M3 |  |  | 7 | 7
26.06.2025 | UNO | 2760 | M3 |  |  | 7 | 7
26.06.2025 | UNO | 2761 | M3 |  |  | 8 | 8
26.06.2025 | UNO | 2763 | M3 |  |  | 4 | 4
26.06.2025 | UNO | 2764 | M3 |  |  | 6 | 6
04.08.2025 | UNO |  | M3 |  |  | 107 | 107 |  |  | 95
605
manth of jun 2nd half |  |  |  | 0 | 0 | 159 | 159
|  |  | M3 | 191 | 0 | 617